Summary of the Visit of Lakshmipur Sadar Hospital and UHCs, Lakshmipur District

1. We started for Lakshmipur on 11th September 2022 at 2:00 pm by Govt. transport. We arrived Lakshmipur at 9:30 PM. We returned back to Dhaka on 14th September 2022 at 3 pm and reached Dhaka at 10:30 pm.

2. The objectives of the visit were-

a) To perform the baseline health survey of the 100bedded Sadar Hospital, Raipur UHC and Ramganj UHC, discussion about the SSK program and importance of quality of health care with them.

b) To assess the progressive development of the quality of the health care, formation of Quality Improvement Committee (QIC), improvement of the quality by implementing the building blocks of C-J Model in Ramgati UHC and Kamalnagar UHC.

Date: 12/09/22 at 9am; Place: Raipur UHC (50 Bedded)

Activities and Findings:

- Total population:3,13,760, Union: 10

- Cleanliness of the hospital premises is average

- 7 posts including gynae and anesthesia are vacant

- DSF program is running

- X-ray, USG and ECG machine are well functioning

- There are spaces in emergency, SSK Booth and Pharmacy can easily be established there

Recommendations:

- The post of gynae and anesthesia consultant should be filled up immediately

- The local Pouroshova must take part in waste management

- Condemnation Board should work to destroy all unwanted items

Date: 12/09/22 at 1pm; Place: Ramganj UHC (31 Bedded)

Activities and Findings:

- Total population: 3,13,500, Union: 10

- The infra-structure of the hospital building is 50 bedded since 2012. Till now, there is no administrative approval for functioning as 50 bedded hospital

- The post of Gynae and Anaesthesia consultant is filled up, so caesarean section is performed

- There are spaces in emergency, SSK Booth and Pharmacy can easily be established there

Recommendations:

- The posts of 50 bedded human resource should get approved as it is necessary for starting SSK program

- Radiological services are non-functioning due to vacant post of Medical Technologist (Radiology). It should be filled up immediately.

- For better office management, the post of Head Assistant, Cashier and Accountant are very important. All the posts are lying vacant. It should be filled up immediately

Date: 13/09/22 at 9am; Place: Kamalnagar UHC (50 Bedded)

Activities and Findings:

- Discussion meeting regarding SSK program and the importance of quality of the health care and formation of QIC committee.

- Observed the development of UHC's healthcare services while performing a site inspection of the hospital.

- We have seen lot of improvements, such as those we had suggested on our earlier visit, including improvements to the cleanliness, beautification, and waste management systems.

Recommendations:

- For functioning of the OT service, deputation of gynae consultant should be cancelled.

- An anaesthesia consultant already working there. But there is no anesthesia machine and OT table

- It can be replaced from the other UHC where extra machine is available.

Date: 13/09/22 at 1pm; Place: Ramgati UHC (31 Bedded)

Activities and Findings:

- Discussion meeting regarding SSK program and the importance of quality of the health care and formation of QIC committee.

- We observed the progressive development of the healthcare services while performing a site inspection of the hospital like construction of new toilets, effective waste disposal system, beautification of ward and corridors, prepared liberation corner for hospital visitors etc.

Recommendations:

- The post of Gynae consultant should be filled immediately to develop effective maternal health services.

- The bed occupancy rate of the hospital is more than 100%. So, rooftop of the hospital can be used for ward and administrative offices by forming Tin-shed infra-structure.

- There are two places selected for SSK booth and pharmacy which needs reconstruction.

Date: 14/09/22 at 1pm; Place: Civil Surgeon Office

Activities:

- Discussed with him about the SSK program and role of the District Hospital and Upazila Health Complexes as well as the role of the health service providers in SSK.

- The Civil Surgeon was very cordial and he ensured us to provide necessary support to implement SSK services

Date: 14/09/22 at 1pm; Place: 100 Bedded Sadar Hospital

Activities and Findings:

- Though the hospital is 100 bedded, but is running with 50 bedded human resource since 2003. There is another 150 bedded infra-structure building is under construction.

- There are 11 posts of consultants but 6 are vacant including Gynae

- There is no post of cashier, accountant and statistician

- Cleanliness of the hospital premises and indoor was weak

- There are spaces for SSK Booth and Pharmacy close to the emergency department

Recommendations:

- The post creation of human resource of 100 bedded hospital is very essential

- For waste management, involvement of Pouroshova is necessary

- Condemnation Board should work to destroy all unwanted items

- There should be 24/7 facility for caesarean section.