CJ model meeting minors

Date: 07/08/18

Time: 11.30 AM

- Committee Formation

  - Steering Committee- To be formed

  - Technical Committee- Functioning

  - District Coordination Committee- To be formed

- Core committee- Formed

  - TOR of core committee- To be done

  - members

- Contract of National Consultant to be done

- Brain storming meeting of core committee

- Inventory : implementation status: Column: districts upazila

- Fully functional

- Partially

- Not functional

- Performance of institutions/ upazila/ hospitals to be addressed

- Indicators to identify

- Identify the partially functioning facility:

  - arranging a workshop

  - share the status

  - share about challenges

  - vision

  - working plan

- List of documents-materials to be drafted and prepared

  - Concept note update: Immediately

  - National Strategy

  - National Action Plan ( include budget and monetary sources)

  - Guidelines: Manager, members

  - SOPs:  Individual Basis

  - M&E tool (Health System Strengthening tool)

  - BCC materials: Brochures, banners, Posters, Festoons, Videos

  - Notifications: References,

- Calendar preparation:

  - Probable timeline of events

- Use logos in materials.

- Inclusion of CJ Model of OP of CBHC and Hospitals in HPNSP

- Resource Mobilization

  - UNICEF

  - WHO

  - DFID

  - jicA

  - UNFPA

  - CBHC

  - HSM

  - HIS in e-health

  - Revenue/ Working Fund