WIT: 1				(EOC Ward)

Step 1:Selection of Kaizen theme with feasibility check with Matrix Diagram

| Possible KAIZEN Theme | Impact | Urgency | Possibility | Resources | Total Score |
| --- | --- | --- | --- | --- | --- |
| Implementation of partograph | 3 | 3 | 1 | 1 | 8 |
| Improve infection prevention | 3 | 3 | 3 | 2 | 11 |
| Improve ANC service with added component | 3 | 3 | 3 | 3 | 12 |
| Improve post-operative care among the operated patient | 3 | 3 | 2 | 2 | 10 |
| Improve display system of EOC service | 3 | 3 | 2 | 1 | 9 |
| Maintain proper temperature in the word | 3 | 3 | 1 | 0 | 7 |

Step 2: Situation analysis

Kaizen theme: ANC service improved with comprehensive services components.

Data collection method: Data will be collected by a WIT member through exit interview of 30 women who would receive ANC in consecutive 10 days.

| Sl No | Contributing factors | Frequency | Cumulative frequency | Cumulative % |
| --- | --- | --- | --- | --- |
| 1 | Proper fill up not done on ANC card | 24 | 24 | 30 |
| 2 | Per abdominal examination is not done properly | 19 | 43 | 54 |
| 3 | Estimation of Hb% not done | 17 | 60 | 75 |
| 4 | Counseling not done | 9 | 69 | 86 |
| 5 | Medical officer/Consultant is not treated every case | 6 | 75 | 94 |
| 6 | USG is not done in time | 5 | 80 | 100 |

Step 3: Root cause analysis (Fishbone diagram):

- Proper fill up of ANC card not done

No initiative for medical officer

No initiative for good quality

Demand not given for screening

Lack of orientation

Supplied low quality machines

Low quality Wt. machine

Wt. machine is not working properly

Lack of work distribution

Overload of the patient

Limited Time

Screen not supplied

Lack of screening

Privacy not maintained properly

SOP not prepared

Sop not available

Insufficient training

Proper fill up of ANC card not done

Man

Material

Environment

Method

- Per abdominal examination is not done properly

Limited number of MO

No initiative for fund

Demand not given for screening

Lack of initiative of on-the-job training

Fund was not available

Not supplied from the store

Limited sitting arrangement

Lack of work distribution

Overload of the patient

Limitation of time

Screen not supplied

Lack of screening

Privacy not maintained properly

Inadequate training

Lack of on-the-job training

Lack of proper knowledge

Per abdominal examination is not done properly

Man

Material

Environment

Method

- HB% not done

s

Lack of initiative for manpower

Not taken initiative for good quality

Initiative not taken for supervision

Initiative not taken

Not supplied good quality

Low quality Hemoglobinometer

Hemoglobinometer  is not working properly

Shortage of manpower

Overload of the patient

Work distribution is not done

Supervision not done properly

Program not started in time

Delay for investigation

Lack of knowledge

Health education not done properly

Lack of importance about hemoglobin estimation

Estimation of HB% not done properly

Man

Material

Environment

Method

Step 4: Identification of actions/countermeasures

| Root cause | Primary action | Secondary action | Importance | Urgency | Difficulty | Time consumption | Resource availability | Total score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No initiative for medical officer | Arrangement of a female medical officer | Identify one medical officer | 2 | 3 | 2 | 2 | 1 | 10 |
|  |  | Posting of a medical officer | 2 | 2 | 1 | 2 | 2 | 9 |
|  |  | Identify place for sitting arrangement | 2 | 2 | 2 | 1 | 1 | 8 |
| No initiative for good quality weight machine | Arrangement of a good quality weight machine | Identify good quality weight machine | 3 | 3 | 2 | 2 | 2 | 12 |
|  |  | Collection of weight machine | 3 | 3 | 2 | 2 | 2 | 12 |
|  |  | Orientation about the use of weight machine | 3 | 3 | 3 | 2 | 3 | 14 |
| Lack of orientation for fill up of ANC card and abdominal examination | Organize a refresher training for fill up of ANC card and abdominal examination | Identify resource person | 3 | 3 | 2 | 3 | 3 | 14 |
|  |  | Arrange logistic and module | 3 | 3 | 3 | 2 | 2 | 13 |
|  |  | pre and post training arrangement | 3 | 3 | 3 | 3 | 3 | 15 |
| Demand not given for screening | Indenting of screen for privacy | Manage screen | 3 | 3 | 2 | 2 | 2 | 12 |
|  |  | Select place for hanging screen | 3 | 3 | 3 | 2 | 3 | 14 |
|  |  | Arrange logistics for hanging | 3 | 3 | 3 | 2 | 2 | 13 |
| No initiative of fund for sitting arrangement | Manage fund for sitting arrangement | Identify the required number of chairs | 3 | 2 | 2 | 2 | 2 | 11 |
|  |  | Identify the probable cost of the chairs | 3 | 3 | 2 | 2 | 1 | 11 |
|  |  | Identify the donors for the support | 3 | 3 | 1 | 1 | 1 | 9 |
| Lack of initiative for manpower for hemoglobin estimation | Arrange one MT lab manpower | Identify one MT lab | 3 | 3 | 1 | 1 | 1 | 9 |
|  |  | Posting of a MT lab | 3 | 3 | 1 | 1 | 1 | 9 |
|  |  | Identify place for sitting arrangement | 3 | 3 | 1 | 1 | 1 | 9 |
| Not taken initiative for good quality Hemoglobinometer | Indenting of good quality Hemoglobinometer | Identify specification of Hemoglobinometer | 3 | 3 | 2 | 1 | 1 | 10 |
|  |  | Identify the handler person | 3 | 2 | 1 | 2 | 2 | 10 |
|  |  | Orientation about the use of the equipment | 3 | 2 | 2 | 2 | 1 | 10 |
| Initiative not taken for supervision of hemoglobin estimation | Organize regular supervision system | Identify the person supervises regularly | 3 | 3 | 3 | 2 | 2 | 13 |
|  |  | Make a checklist for quality investigation | 3 | 3 | 3 | 2 | 2 | 13 |
|  |  | Ensure regular on-the-job training | 3 | 3 | 3 | 2 | 2 | 13 |
| Initiative not taken for health education | Arrange effective health education session | Identify the topics for health education | 3 | 3 | 3 | 2 | 2 | 13 |
|  |  | Identify the health educator | 3 | 3 | 2 | 2 | 2 | 12 |
|  |  | Regular monitoring of health education | 3 | 3 | 2 | 2 | 2 | 12 |

Step 5: Implementation of actions/countermeasures: action plan and progress monitoring for EOC ward (WIT-1)

| Sl | Actions | Where | Who | When | Date of monitoring | Who | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Identify good quality weight machine | EOC ward | Consultant | 20 to 30 Nov | 28 Nov | RMO |  |
| 2 | Collection of weight machine | EOC ward | Hospital Super | 30 Nov to 15 Dec | 10 Dec | Super |  |
| 3 | Orientation about the use of weight machine | EOC ward | Consultant | 15 to 20 Dec | 18 Dec | Focal Person |  |
| 4 | Identify resource person | EOC ward | Consultant | 20 to 30 Nov | 25 Nov | Focal Person |  |
| 5 | Arrange logistic and module | EOC ward | RMO | 20 Nov to 10 Dec | 5 Dec | Focal Person |  |
| 6 | pre and post training arrangement | EOC ward | Consultant | 25 Nov to 5 Dec | 30 Nov | RMO |  |
| 7 | Manage screen | EOC ward | Store keeper | 25 Nov to 15 Dec | 30 Nov | RMO |  |
| 8 | Select place for hanging screen | EOC ward | Team Leader | 15 Nov to 20 Dec | 17 Dec | Focal Person |  |
| 9 | Arrange logistics for hanging | EOC ward | Team Leader | 15 Dec to 20 Dec | 17 Dec | Focal Person |  |
| 10 | Identify the person supervises regularly | EOC ward | RMO | 25 to 30 Nov | 28 Nov | Super |  |
| 11 | Make a checklist for quality investigation | EOC ward | RMO | 25 Nov to 10 Dec | 5 Dec | Super |  |
| 12 | Ensure regular on-the-job training | EOC ward | Hospital Super | 30 Nov to 15 Dec | 10 Dec | Super |  |
| 13 | Identify the topics for health education | EOC ward | Consultant | 25 Nov to 30 Nov | 28 Nov | Focal Person |  |
| 14 | Identify the health educator | EOC ward | RMO | 25 Nov to 30 Nov | 27 Nov | Super |  |
| 15 | Regular monitoring of health education | EOC ward | Hospital Super | 1 to 30 Dec | 15 Dec | Super |  |

Step 6: Effectiveness of actions/countermeasures

| Sl No | Contributing factors | Frequency |  | Frequency Reduction | Reduced% |
| --- | --- | --- | --- | --- | --- |
|  |  | Before PDCA | After PDCA |  |  |
| 1 | Proper fill up not done on ANC card | 24 | 10 | 14 | 58% |
| 2 | Per abdominal examination is not done properly | 19 | 7 | 12 | 63% |
| 3 | Estimation of Hb% not done | 17 | 5 | 12 | 71% |
| 4 | Counseling not done | 9 | 3 | 6 | 67% |
| 5 | Medical officer/Consultant is not treated every case | 6 | 2 | 4 | 67% |
| 6 | USG is not done in time | 5 | 0 | 5 | 100% |