WIT: 1				(EOC Ward)

Step 1:Selection of Kaizen theme with feasibility check with Matrix Diagram

| Possible KAIZEN Theme | Impact to patient outcome | Affordable in terms of time and resources | Easy to measure | Under control of team members. | Total Score |
| --- | --- | --- | --- | --- | --- |
| Implementation of partograph | 5 | 3 | 3 | 4 | 15 |
| Improve infection prevention | 5 | 3 | 2 | 2 | 12 |
| Improve labour room service with added component | 5 | 5 | 5 | 4 | 19 |
| Improve post-operative care among the operated patient | 4 | 4 | 3 | 3 | 14 |
| Maintain proper temperature, pulse, BP in the word | 4 | 4 | 4 | 5 | 17 |

Step 2: Situation analysis

Kaizen theme: Labor room service improved with comprehensive services components.

Data collection method: Data will be collected by a WIT member through exit interview of 30 women who will deliver in consecutive 10 days from 4th to 14th May.

| Sl No | Contributing factors | Frequency | Cumulative frequency | Cumulative % |
| --- | --- | --- | --- | --- |
| 1 | Sterile delivery set not used properly | 34 | 34 | 40% |
| 2 | Labor room sister is not available. | 15 | 49 | 63% |
| 3 | Chlorine solution is not used properly | 12 | 61 | 71% |
| 4 | Counseling is not done | 10 | 71 | 84% |
| 5 | Medical officer/Consultant is not supervise every case | 6 | 77 | 90% |
| 6 | Labor room lighting system not functioning effectively | 5 | 82 | 96% |
| 7 | Privacy is not maintained properly | 3 | 85 | 100% |

Step 3: Root cause analysis (Fishbone diagram):

- Sterile delivery set not used properly

Job description is not developed

Not perched the set

Not available in store

Not collected  from store

Number of delivery set is limited

Division of  labour not done

Overload of the patients

Under utiliztion of manpower

Lack of importance of delivery  set

Sterile delivery set not used properly

Man

Material

Environment

Method

- Labor room sister is not available.

Limited number of nurses

No initiative for fund

Demand not given for screening

Lack of initiative of on-the-job training

Fund was not available

Not supplied from the store

Limited sitting arrangement

Lack of work distribution

Overload of the patient

Limitation of time

Screen not supplied

Lack of screening

Privacy not maintained properly

Inadequate training

Lack of on-the-job training

Lack of proper knowledge

Labor room sister is not available.

Man

Material

Environment

Method

- Chlorine  solution is not used properly

Lack of initiative for manpower

Chlorine is not perched

Initiative not taken for supervision

Initiative not taken

Chlorine  supplies is limited

Indent is not given in proper time

Irregular supplies of chlorine

Shortage of manpower

Overload of the patient

Work distribution is not done

Supervision not done properly

Preparation not started in time

Delay for preparation

Lack of knowledge

Health education not done properly

Lack of importance about chlorine solution

Chlorine solution is not used properly.

Man

Material

Environment

Method

- Counseling is not done

- Counseling is not done

Man

Material

Environment

Method

Step 4: Identification of actions/countermeasures

| Root cause | Primary action | Secondary action | Importance | Urgency | Difficulty | Time consumption | Resource availability | Total score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Step 5: Implementation of actions/countermeasures: action plan and progress monitoring for EOC ward (WIT-1)

| Sl | Actions | Where | Who | When | Date of monitoring | Who | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Identify good quality weight machine | EOC ward | Consultant | 20 to 30 Nov | 28 Nov | RMO |  |
| 2 | Collection of weight machine | EOC ward | Hospital Super | 30 Nov to 15 Dec | 10 Dec | Super |  |
| 3 | Orientation about the use of weight machine | EOC ward | Consultant | 15 to 20 Dec | 18 Dec | Focal Person |  |
| 4 | Identify resource person | EOC ward | Consultant | 20 to 30 Nov | 25 Nov | Focal Person |  |
| 5 | Arrange logistic and module | EOC ward | RMO | 20 Nov to 10 Dec | 5 Dec | Focal Person |  |
| 6 | pre and post training arrangement | EOC ward | Consultant | 25 Nov to 5 Dec | 30 Nov | RMO |  |
| 7 | Manage screen | EOC ward | Store keeper | 25 Nov to 15 Dec | 30 Nov | RMO |  |
| 8 | Select place for hanging screen | EOC ward | Team Leader | 15 Nov to 20 Dec | 17 Dec | Focal Person |  |
| 9 | Arrange logistics for hanging | EOC ward | Team Leader | 15 Dec to 20 Dec | 17 Dec | Focal Person |  |
| 10 | Identify the person supervises regularly | EOC ward | RMO | 25 to 30 Nov | 28 Nov | Super |  |
| 11 | Make a checklist for quality investigation | EOC ward | RMO | 25 Nov to 10 Dec | 5 Dec | Super |  |
| 12 | Ensure regular on-the-job training | EOC ward | Hospital Super | 30 Nov to 15 Dec | 10 Dec | Super |  |
| 13 | Identify the topics for health education | EOC ward | Consultant | 25 Nov to 30 Nov | 28 Nov | Focal Person |  |
| 14 | Identify the health educator | EOC ward | RMO | 25 Nov to 30 Nov | 27 Nov | Super |  |
| 15 | Regular monitoring of health education | EOC ward | Hospital Super | 1 to 30 Dec | 15 Dec | Super |  |

Step 6: Effectiveness of actions/countermeasures

| Sl No | Contributing factors | Frequency |  | Frequency Reduction | Reduced% |
| --- | --- | --- | --- | --- | --- |
|  |  | Before PDCA | After PDCA |  |  |
| 1 | Sterile delivery set not used properly | 34 | 10 | 24 | 71% |
| 2 | Labor room sister is not available. | 15 | 3 | 12 | 80% |
| 3 | Chlorine solution is not used properly | 12 | 2 | 10 | 83% |
| 4 | Counseling is not done | 10 | 3 | 7 | 70% |
| 5 | Medical officer/Consultant is not supervise every case | 6 | 1 | 5 | 83% |
| 6 | Labor room lighting system not functioning effectively | 5 | 1 | 4 | 80% |
| 7 | Privacy is not maintained properly | 3 | 0 | 3 | 100% |