মানসম্পন্ন সেবাদানের কর্ম পরিকল্পনা

১. উদ্দেশ্যসমূহ (Objectives)

- চৌগাছা-ঝিনাইদহ আদর্শের মাপকাঠিতে SSK ভুক্ত সকল জেলা-উপজেলা হাসপাতালে প্রাথমিক জরীপকাজ সম্পন্ন করা।

- SSK ভুক্ত নির্ধারিত †Rjv-Dc‡Rjv nvmcvZvলগুলোতে ‡PŠMvQv-wSbvB`n Av`র্শ বাস্তবায়ন করা।

২. লক্ষ্যমাত্রা (Target)

- ২০২৩ সালের ৩০শে জুনের মধ্যে টাঙ্গাইল জেলার সকল উপজেলা এবং বরগুনায়, লক্ষ্মীপুর, বরিশাল, মানিকগঞ্জ, লালমনিরহাট ও কুড়িগ্রাম জেলার কমপক্ষে একটি উপজেলায় চৌগাছা-ঝিনাইদহ (সি-জে) মডেলের আলোকে কার্যক্রম সম্প্রসারণের ব্যবস্থা করা।

- SSK ভুক্ত প্রতিটি জেলা ও উপজেলা হাসপাতালে্র মানোন্নয়নে প্রাথমিক জরীপ সম্পন্ন করা

- সি-জে মডেলের আলোকে স্বাস্থ্য কমপ্লেক্সগুলোতে Quality Improvement Committee (QIC) এবং Work Improvement Team (WIT) কমিটি গঠন ও প্রাথমিক কার্যক্রম শুরু করা।

- প্রতিটি জেলা ও উপজেলা হাসপাতালে স্থানীয়ভাবে মডেলের কিছু কিছু বৈশিষ্টের বাস্তবায়ন করা।

৩. এ যাবত নেয়া কার্যক্রম (১লা এপ্রিল থেকে)

- জরীপের জন্য প্রশ্নমালা প্রস্তুতকরন। (এপ্রিল-২০২২)

- প্রথম পর্যায়ের টাঙ্গাইল জেলার জেলা হাসপাতালসহ সকল উপজেলা হাসপাতাল পরিদর্শন সম্পন্ন

(এপ্রিল, ২০২২ থেকে জুন, ২০২২) ।

- সাতটি জেলার মধ্যে তিনটি জেলায় SSK কার্যক্রম বাস্তবায়নে প্রাথমিক পর্যায়ে জেলা-উপজেলা পর্যায়ে কর্মকর্তা এবং জনপ্রতিনিধিদের সাথে SSK কার্যক্রম বাস্তবায়ন সংক্রান্ত আলোচনা সম্পন্ন। (জুন-আগস্ট,২০২২)

- SSK টিমের সাথে কর্মকৌশলের বাস্তবায়ন সংক্রান্ত আলোচনা সম্পন্ন। (জুলাই,২০২২)

- বরগুনা জেলার সদর হাসপাতাল এবং ৫টি উপজেলা স্বাস্থ্য কমপ্লেক্স এর প্রাথমিক জরীপকাজ সম্পন্ন। (২২-২৫ আগস্ট ২০২২)

- লক্ষ্মীপুর জেলার সদর হাসপাতাল এবং রায়পুর ও রামগঞ্জ উপজেলা স্বাস্থ্য কমপ্লেক্স এর প্রাথমিক জরীপকাজ সম্পন্ন এবং কমলনগর ও রামগতি উপজেলা স্বাস্থ্য কমপ্লেক্সে Quality Improvement Committee (QIC) গঠন। (১১-১৪ সেপ্টেম্বর ২০২২)

- চৌগাছা-ঝিনাইদহ মডেলের আলোকে SSK কার্যক্রমে যে সব জেলা-উপজেলায় স্বাস্থ্যসেবার উন্নয়ন করা হবে, সেখানে স্বল্প ও মধ্য মেয়াদে জেলা ও উপজেলা চিহ্নিত করা।

    - যারা এই কাজ করবে তাদের নিয়ে স্বাস্থ্য অর্থনীতি ইউনিটের পরিচালক (গবেষনা) এর সাথে বৈঠক এবং নিয়মিত পর্যালোচনা করা

    - অবস্থিত ব্যবস্থার সাথে কোন কোন উপাদান যোগ করা হবে তা নির্ধারণ করা।

    - খরচের হিসাব প্রস্তুত করা

    - প্রশিক্ষণ ম্যানুয়াল প্রস্তুত করা এবং তা পরীক্ষা করা

    - ক্লাস রুম প্রশিক্ষণের সাথে মেন্টরিং পদ্ধতির মিশ্রণ ঘটানো

    - সকল পক্ষের অংশগ্রহণে মাঠ পর্যায়ে উদ্বুদ্ধকরণ সভা আয়োজন

    - নিয়মিত তথ্য সংগ্রহ, পর্যবেক্ষণ, পরিবীক্ষণ করে উন্নতি পর্যালোচনা করা

৪. স্বাস্থ্যসেবার মানোন্নয়নের ধাপসমূহ:

- জরিপ সম্পাদনের মাধ্যমে একটি প্রাথমিক মূল্যায়ন প্রতিবেদন তৈরী করা

- চৌগাছা-ঝিনাইদহ মডেলের বিল্ডিং ব্লকের আলোকে প্রতিষ্ঠানের সমস্যাসমূহ চিহ্নিত করা।

- প্রতিটি প্রতিষ্ঠানের জন্য নির্দিষ্ট লক্ষ্যমাত্রা (Target) নির্ধারণ করা এবং তা বাস্তবায়নে সেবাদানকারীদের অঙ্গীকার (Commitment) অর্জন করা।

- মানসম্পন্ন স্বাস্থ্যসেবার লক্ষ্যে উন্নত কর্মপরিবেশ গড়ে তোলা।

- প্রতিষ্ঠানে Quality Improvement Committee (QIC) এবং Work Improvement Team (WIT) টিমসমূহ গঠন করা।

- মানসম্পন্ন সেবাদান বাস্তবায়নে 5S-KAIZEN পদ্ধতি বাস্তবায়ন করা। এই সংক্রান্ত একটি কর্মশালার ব্যবস্থা করা।

- চৌগাছা-ঝিনাইদহ মডেলের বিল্ডিং ব্লক্সমূহ বাস্তবায়নের লক্ষ্যে SOP প্রস্তুতকরণ

- স্বাস্থ্য সেবাদানকারীদের চৌগাছা-ঝিনাইদহ স্বাস্থ্য প্রতিষ্ঠান পরিদর্শনের মাধ্যমে বাস্তব অভিজ্ঞতা অর্জনের ব্যবস্থা করা।

- উপজেলা SSK কমিটিকে সক্রিয় করা এবং কার্যক্রমের অগ্রগতি মূল্যায়ন করা।

৫. সি-জে মডেল বাস্তবায়ন উপজেলা স্বাস্থ্য কমপ্লেক্স (QIC)কমিটি

| ক্রমিক | কর্মকর্তা/ জনপ্রতিনিধির পদবী | কমিটিতে পদ |
| --- | --- | --- |
|  | উপজেলা স্বাস্থ্য ও পরিবার পরিকল্পনা কর্মকর্তা | চেয়ারপারসন |
|  | আবাসিক মেডিক্যাল অফিসার | সদস্য সচিব ও ফোকাল পারসন |
|  | ডাব্লুআইটি কমিটিসমূহের টিম লিডার ও ফ্যাসিলিটেটরগণ | সদস্য |

কর্মপরিধি

- প্রতি মাসে একবার সভা অনুষ্ঠান করবে

- কমিউনিটি হতে কোন্ ধরণের সহযোগিতা নেবে তার সুপারিশ তৈরী করবে

- প্রতিটি ডাব্লুআইটি কার্যক্রমের বাস্তবায়নের অগ্রগতি মূল্যায়ন করবে

- ঊর্ধতন কর্তৃপক্ষকে মাসের প্রথম সপ্তাহে নির্ধারিত ছকে প্রতিবেদন প্রেরণ করবেন

৬. সি-জে মডেল বাস্তবায়ন উপজেলা স্বাস্থ্য কমপ্লেক্স এর প্রতিটি ওয়ার্ডে (WIT)কমিটি

| ক্রমিক | কর্মকর্তা/ জনপ্রতিনিধির পদবী | কমিটিতে পদ |
| --- | --- | --- |
|  | আবাসিক মেডিক্যাল অফিসার/কনসালটেন্ট | টিম লিডার |
|  | ওয়ার্ড ইনচার্জ নার্স/মেডিকেল এসিস্টেন্ট, অফিস সহকারি | সদস্য সচিব |
|  | ওয়ার্ডের সকল নার্স, আয়া, ওয়ার্ডবয়, ক্লিনার | সদস্য |

কর্মপরিধি

- প্রতি সপ্তাহে অফিস শুরুর ১৫ মিনিট স্থায়ী একবার সভা অনুষ্ঠান করবে

- কমিউনিটি হতে কোন্ ধরণের সহযোগিতা নেবে তার সুপারিশ তৈরী করবে

- ওয়ার্ডের সমস্যা চিহ্নিত করা ও বাস্তবায়নের অগ্রগতি মূল্যায়ন করবে

- ঊর্ধতন কর্তৃপক্ষকে প্রতি সপ্তাহে QIC কে নির্ধারিত ছকে প্রতিবেদন প্রেরণ করবেন

৭. প্রাতিষ্ঠানিক বাস্তবায়নসূচী:

| নং | কর্মসূচি | বাস্তবায়নকারী | সময়সীমা |
| --- | --- | --- | --- |
|  | QIC এবং WIT কমিটি গঠ্ন | স্থানীয় হাসপাতাল/উপজেলা স্বাস্থ্য কমপ্লেক্স কর্তৃপক্ষ | ৭ দিন |
|  | প্রাথমিক মূল্যায়ন প্রতিবেদন প্রস্তুতকরণ | কিউআইসি ও ডাব্লুআইটি দল | ১০ দিন |
|  | সমস্যাসমূহ চিহ্নিতকরণ | কিউআইসি ও ডাব্লুআইটি দল | ১৫ দিন |
|  | লক্ষ্য এবং লক্ষ্যমাত্রা নির্ধারণ | কিউআইসি দল | ৫ দিন |
|  | লক্ষ্যসমূহ বাস্তবায়নে জনগোষ্ঠী ও সেবাদানকারীদের অঙ্গিকার অর্জনে কর্মশালার মাধ্যমে উদ্বুদ্ধকরণ | স্থানীয় হাসপাতাল/উপজেলা স্বাস্থ্য কমপ্লেক্স কর্তৃপক্ষ | ৩০ দিন |
|  | প্রয়োজনীয় সামগ্রীর তালিকা প্রস্তুত ও সংগ্রহ | স্থানীয় হাসপাতাল/উপজেলা স্বাস্থ্য কমপ্লেক্স কর্তৃপক্ষ | ২০ দিন |
|  | মূল্যবোধভিত্তিক কর্মপরিবেশ ও প্রাতিষ্ঠানিক সংস্কৃতি গড়ে তোলার নীতিমালা প্রস্তুত করা | কিউআইসি দল | ৩০ দিন |
|  | লক্ষ্য বাস্তবায়নে সামাজিক আন্দোলন গড়ে তোলার জন্য সকল অংশীজনের সাথে মতবিনিময় | কমিউনিটি সহায়তা গ্রুপ ও স্থানীয় স্বাস্থ্য কর্তৃপক্ষ | ৩০ দিন |
|  | মানসম্পন্ন সেবাদানে ৫এস কাইজেন পদ্ধতি বিষয়ে প্রশিক্ষণ | স্থানীয় স্বাস্থ্য কর্তৃপক্ষ | ৭ দিন |
|  | প্রতিটি প্রশিক্ষণার্থী দল কর্তৃক চৌগাছা ও ঝিনাইদহ স্বাস্থ্য প্রতিষ্ঠান পরিদর্শনের মাধ্যমে বাস্তব জ্ঞান অর্জন | জাতীয় টেকনিক্যাল কমিটি | --------- |
|  | মডেল সম্পর্কে অভিজ্ঞ বিশেষজ্ঞ দল কর্তৃক স্বাস্থ্য প্রতিষ্ঠানে মডেল হাতে কলমে বাস্তবায়নের জন্য সফর | জাতীয় টেকনিক্যাল কমিটি | ৭ দিন |
|  | কার্যক্রমের অগ্রগতি মূল্যায়ন | স্থানীয় স্বাস্থ্য কর্তৃপক্ষ | প্রতি ৪৫ দিন অন্তর |

Checklist  to asses the progress 0f quality of are of UHC.

| Sl.No. | Building blocks of C-J Model | Satisfactory | Average | Unsatisfactory |
| --- | --- | --- | --- | --- |
| 1. | Cycle stand close to the main gate |  |  |  |
| a. | A shed with sufficient space |  |  |  |
| b. | Human resource for shed |  |  |  |
| c. | Close to the main gate |  |  |  |
| d. | Management system. |  |  |  |
| 2. | Health Education Session. |  |  |  |
| a. | Appropriate location |  |  |  |
| b. | Sitting arrangement |  |  |  |
| c. | Person (2 educators) |  |  |  |
| d. | Roster of health education. |  |  |  |
| e. | Registrar to mention no. of persons present in sessions |  |  |  |
| f. | Presence audio-visual system |  |  |  |
| 3 | Cleanliness & beautification |  |  |  |
| a. | Cleanliness in front of the gate |  |  |  |
| b. | Campus |  |  |  |
| c. | Outdoor incuding toilets. |  |  |  |
| d. | Emergency |  |  |  |
| e. | Indoor including toilets |  |  |  |
| f. | OT |  |  |  |
| g. | Rooftop of the hospital building |  |  |  |
| h. | Garden in the campus |  |  |  |
| i. | Waste management system |  |  |  |
| 4. | Separation of patients in out door & indoor |  |  |  |
| A | Male |  |  |  |
| b. | Female |  |  |  |
| c. | EOC. |  |  |  |
| d. | Pediatric |  |  |  |
| 5. | Blood doner list with 24/7 B.T facility |  |  |  |
| a. | 24/7 hours available Medical technologist (Lab) |  |  |  |
| b. | Registrar of donor list with Mob. No. |  |  |  |
| c. | List of number of blood donor >500. |  |  |  |
| d. | Presence of reagents for grouping |  |  |  |
| e. | Screenig facility |  |  |  |
| 6. | Birth- death recording |  |  | 1 |
| A | Presence of data collection format |  |  |  |
| b. | Review some format |  |  |  |
| c. | Live births record (last one month) |  |  |  |
| d. | Hospital death review in last one month |  |  |  |
| e.1 | Maternal death (last one month) |  |  |  |
| e.2 | 0-28 days death (last one month) |  |  |  |
| e.3 | 29 days - 1 yr death (last one month) |  |  |  |
| e.4 | 1-5yrs.death(last one month) |  |  |  |
| 7. | Reception desk |  |  |  |
| a. | Apropriate location & arragement |  |  |  |
| b. | Human resource |  |  |  |
| c. | Communication capacity of HR |  |  |  |
| 8. | Developed Emergency dept. |  |  |  |
| a. | Arrangement of tables. |  |  |  |
| b. | Infection control system |  |  |  |
| c. | Maitenance of privacy. |  |  |  |
| d. | Toilet facility |  |  |  |
| e. | Presence oxygen facility |  |  |  |
| f. | Nebulization facility |  |  |  |
| g. | Functioning Succer machine |  |  |  |
| h. | Presence of weleqiped emergency kitbox. |  |  |  |
| 9. | 5S –KAIZEN implementation. |  |  |  |
| a. | Orientation on quality of care. |  |  |  |
| b. | Formation QIC Comette |  |  |  |
| c. | Formation of WIT Comette. |  |  |  |
| d. | Orientation on 5 S KAIZEN-TQM |  |  |  |
| e. | Monthly meeting of QIC commette. |  |  |  |
| f. | Weekly meeting of WIT comette. |  |  |  |
| g. | Innovation in last month. |  |  |  |
| 10. | Community Participation. |  |  |  |
| a. | Participation of the Upazilla Parisad. |  |  |  |
| b. | Participation of the Pourosova |  |  |  |
| c. | Functioning of the Social Welfare Comette |  |  |  |
| d. | Participation of officer’s club. |  |  |  |
| e. | Human resource support from the community. |  |  | 2 |
| f. | Logistic support from the community. |  |  |  |
| 11. | Corner based Service. |  |  |  |
| a. | ANC&PNC Corner for pregnant mother |  |  |  |
| b. | MCI corner for Under-5 children. |  |  |  |
| c. | NCD corner for non-communicable disesed patients |  |  |  |
| d. | ORT corner |  |  |  |
| e. | EPI & Breastfeeding corner |  |  |  |
| f. | Health education corner. |  |  |  |
| g. | Adlecence corner |  |  |  |
| h. | VIA-Corner |  |  |  |
| 12. | Display.of hospital services. |  |  |  |
| a. | UH&FPO room. |  |  |  |
| b. | Emergency |  |  |  |
| c. | Every corner |  |  |  |
| d. | Every ward: Male, female, Pedriatric, labour, OT |  |  |  |
| 13. | Cash counter for receiving Govt money. |  |  |  |
| a. | Formation of a Cash counter for all diagnostic services. |  |  |  |
| b. | Site selection |  |  |  |
| C | Human resource |  |  |  |
| 14. | Devolped labour ward. |  |  |  |
| A. | ANC & PNC (OPD) Serice. |  |  |  |
| a. | ANC visit (Minimum 5visit) & 2PNC visit |  |  |  |
| b. | ANC card fuifilled properly. |  |  |  |
| c. | Proper recording system |  |  |  |
| d. | Final treatmeant must be given by gynae&obs trained M.O. |  |  |  |
| B. | Labour ward (Indoor) |  |  |  |
| a. | Presence of sufficient Midwives. |  |  |  |
| b. | Sufficient labour tables |  |  |  |
| c. | Sufficens equipments. |  |  |  |
| d. | Infection control system. |  |  |  |
| e. | Eclumpsia Kit |  |  |  |
| f. | PPH Kit |  |  |  |
| g. | Baby resuscitation kit |  |  |  |
| h. | Toilet facility. |  |  |  |
| i. | Bed facility. |  |  |  |
| j. | Maintenance of privacy |  |  | 3 |
| k. | Quality of the Midwives on conducting NVD. |  |  |  |
| l. | Presence of 24/7 gynae & obs trained doctor in campus. |  |  |  |
| m. | Presence of labour ward incharge SSN in campus. |  |  |  |
| C. | Devloped OT Facility |  |  |  |
| a. | Well equiped Gynae & Obs.OT |  |  |  |
| b. | Infection control system |  |  |  |
| c. | Presence of gynae & obs. Surgeon 24/7 in campus. |  |  |  |
| d. | Presence of Anesthesiologist 24/7 in campus |  |  |  |
| e. | Presnce of OT inchchargr SSN 24/7 in campus. |  |  |  |
| f. | Emergency kitbox |  |  |  |
| g. | Well equiped Post operative ward. |  |  |  |
| 15. | Devolped paediatric health |  |  |  |
| A. | Development in IMCI corner having the services (GOBI-FF) |  |  |  |
| a. | Asses the neutritional status. |  |  |  |
| b. | Breast feeding. |  |  |  |
| c. | Idea about oral rehydration therapy in dirrhoea. |  |  |  |
| d. | Immunization of the baby. |  |  |  |
| e. | Mother receving F.P method. |  |  |  |
| d. | Treatnent of the disease. |  |  |  |
| B. | Treatment in indoor having |  |  |  |
| a. | Effective neonatal care facility. |  |  |  |
| a.1 | Capable of neonatal I/V transfusion. |  |  |  |
| a.2 | Capable of neonatal resuscitation. |  |  |  |
| a.3 | Presence pedatrician 24/7 within campus. |  |  |  |
| 16. | Devloped diagnostic Service |  |  |  |
| a. | Functioning USG machine. |  |  |  |
| b. | Functioning digital X-ray. |  |  |  |
| c. | Functioning ECG machine |  |  |  |
| e. | Functioning blood bank |  |  |  |
| f. | Functioning lab. |  |  |  |
| f.1. | Hematology |  |  |  |
| f.2. | Biochemistry |  |  |  |
| f.3 | Hormones & Immunology |  |  |  |
| f.4. | Linical pathology. |  |  | 4 |
| 17. | Position in HSS score (Satisfactory <100, Average 100-200, Unsatisfactory >200. |  |  |  |
| 18. | Power point Presentation &Video on UHC |  |  |  |
| A. | Power Point Presentation having |  |  |  |
| a. | Vision |  |  |  |
| b. | Background history |  |  |  |
| c | Health profile |  |  |  |
| d. | Minimumlast 4 years major services performances. |  |  |  |
| e. | SSK performance & progress. |  |  |  |
| f. | Hospital services by photo. |  |  |  |
| g. | Positve changes showing before after situtation by photo& phycal verification |  |  |  |
| h. | Innvation activites |  |  |  |
| i. | Acheivement/Recognations |  |  |  |
| j. | Psitive information in media. |  |  |  |
| k. | Challenges of the hospital. |  |  |  |
| l. | Future plan (Waya forward) |  |  |  |
| B | Video on UHC. |  |  |  |
| a. | Duration -not morethan 4 minutes |  |  |  |
| b. | Covers all major services. |  |  |  |
| c. | Succes stoty |  |  |  |
| d. | Comments of 2 patients, local Mp, Mayor, CivilSurgeon, UNO, UH&FPO |  |  |  |
| 19. | Knowledge about 8th Five Year plan & SDG. |  |  |  |
| a. | Orientatio on health related 8th 5 yr plan& S.D.G.(Targets & Goal) |  |  |  |
| b. | Display in billboard. |  |  |  |
| c. | Discimmation of idea that how the service provider can calculate |  |  |  |
| d. | Display of yearly progress |  |  |  |
| 20. | Zero-Tollarance on corruption |  |  |  |
| a. | Discussion on moral based enveroment |  |  |  |
| b. | Discussion on patients right. |  |  |  |
| c. | Maintenance of morality. |  |  |  |
| 21. | SSK |  |  |  |
| A. | SSK Human Resourses |  |  |  |
| a. | Ensureing the services of the guards |  |  | 5 |
| b. | Ensureing the services of the cleaner |  |  |  |
| B. | SSK Booth Functions. |  |  |  |
| C | Functions of SSK Pharmacy |  |  |  |
| D | SSK patients services in Indoor. |  |  | 6 |

| - 1. | Cycle stand close to the main gate |  |  |  |
| --- | --- | --- | --- | --- |
| - a. | A shed with sufficient space |  |  |  |
| - b. | Human resource for shed |  |  |  |
| - c. | Close to the main gate |  |  |  |
| - d. | Management system. |  |  |  |
| - 2. | Health Education Session. |  |  |  |
| - a. | Appropriate location |  |  |  |
| - b. | Sitting arrangement |  |  |  |
| - c. | Person(2 educators) |  |  |  |
| - d. | Roster of health education. |  |  |  |
| - e. | Registrar to mention no. of persons present in session |  |  |  |
| - f. | Presence audio-visual system |  |  |  |
| - 3 | Cleanliness & beautification |  |  |  |
| - a. | Cleanliness in front of the gate |  |  |  |
| - b. | Campus |  |  |  |
| - c. | Outdoor incuding toilets. |  |  |  |
| - d. | Emergency |  |  |  |
| - e. | Indoor including toilets |  |  |  |
| - f. | OT |  |  |  |
| - g. | Rooftop of the hospital building |  |  |  |
| - h. | Garden in the campus |  |  |  |
| - i. | Waste management system |  |  |  |
| - 4. | Separation of patients in out door & indoor |  |  |  |
| - A | Male |  |  |  |
| - b. | Female |  |  |  |
| - c. | EOC. |  |  |  |
| - d. | Pediatric |  |  |  |
| - 5. | Blood doner list with 24/7 B.T facility |  |  |  |
| - a. | 24/7 hours available medical technologist (Lab) |  |  |  |
| - b. | Registrar of donor list with Mob. No. |  |  |  |
| - c. | List of number of blood donor >500. |  |  |  |
| - d. | Presence of reagents for grouping |  |  |  |
| - e. | Screenig facility |  |  |  |
| - 6. | Birth- death recording |  |  |  |
| - A | Presence of data collection format |  |  |  |
| - b. | Review some format |  |  |  |
| - c. | Live births record(last one month) |  |  |  |
| - d. | Hospital death review in last one month |  |  |  |
| - e.1 | Maternal death (last one month) |  |  |  |
| - e.2 | 0-28 days death(last one month) |  |  |  |
| - e.3 | 29 days - 1 yr death(last one month) |  |  |  |
| - e.4 | 1-5yrs.death(last one month) |  |  |  |
| - 7. | Reception desk |  |  |  |
| - a. | Apropriate location & arragement |  |  |  |
| - b. | Human resource |  |  |  |
| - c. | Communication capacity of HR |  |  |  |
| - 8. | Developed Emergency Dept. |  |  |  |
| - a. | Arrangement of tables. |  |  |  |
| - b. | Infection control system |  |  |  |
| - c. | Maitenance of privacy. |  |  |  |
| - d. | Toilet facility |  |  |  |
| - e. | Presence oxygen facility |  |  |  |
| - f. | Nebulization facility |  |  |  |
| - g. | Functioning Succer machine |  |  |  |
| - h. | Presence of weleqiped emergency kitbox. |  |  |  |
| - 9. | 5S –KAIZEN implementation. |  |  |  |
| - a. | Orientation on quality of care. |  |  |  |
| - b. | Formation QIC Comette |  |  |  |
| - c. | Formation of WIT Comette. |  |  |  |
| - d. | Orientation on 5 S KAIZEN-TQM |  |  |  |
| - e. | Monthly meeting of QIC commette. |  |  |  |
| - f. | Weekly meeting of WIT comette. |  |  |  |
| - g. | Innovation in last month. |  |  |  |
| - 10. | Community Participation. |  |  |  |
| - a. | Participation of the Upazilla Parisad. |  |  |  |
| - b. | Participation of the Pourosova |  |  |  |
| - c. | Functioning of the Social Welfare Comette |  |  |  |
| - d. | Participation of officers club. |  |  |  |
| - e. | Human resource support from the community. |  |  |  |
| - f. | Logistic support from the community. |  |  |  |
| - 11. | Cornerbased Service. |  |  |  |
| - a. | ANC&PNC Corner for pregnant mother |  |  |  |
| - b. | MCI corner for Under-5 children. |  |  |  |
| - c. | NCD corner for noncommunicable disesed patients |  |  |  |
| - d. | ORT corner |  |  |  |
| - e | EPI & Breast feeding corner |  |  |  |
| - f. | Health education corner. |  |  |  |
| - g. | Adlecence corner |  |  |  |
| - h. | VIA-Corner |  |  |  |
| - 12. | Hospital service display.. |  |  |  |
| - a. | UH&FPO room. |  |  |  |
| - b. | Emergency |  |  |  |
| - c. | Every corner |  |  |  |
| - d. | Every ward: Male,female, Pedriatc,Labour ,OT |  |  |  |
| - 13. | Cash counter for receiving Govt money. |  |  |  |
| - a. | Formation of a Cash counter for all diagnostic services. |  |  |  |
| - b. | Site selection |  |  |  |
| - C | Human resource |  |  |  |
| - 14. | Devolped labour ward. |  |  |  |
| - A. | ANC & PNC (OPD) Serice. |  |  |  |
| - a. | ANC visit( Minimum 5visit)& 2PNC visit |  |  |  |
| - b. | ANC card fuifilled properly. |  |  |  |
| - c. | Proper recording system |  |  |  |
| - d. | Final treatmeant must be taken by gynae&obs trained M.O. |  |  |  |
| - B. | Labour ward.(Indoor) |  |  |  |
| - a. | Presence of sufficient Midwives. |  |  |  |
| - b. | Sufficient labour tables |  |  |  |
| - c. | Sufficens equipments. |  |  |  |
| - d. | Infection control system. |  |  |  |
| - e. | Eclumpsia Kit |  |  |  |
| - f. | PPH Kit |  |  |  |
| - g. | Baby resuscitation kit |  |  |  |
| - h. | Toilet facility. |  |  |  |
| - i. | Bed facility. |  |  |  |
| - j. | Maintenance of privacy |  |  |  |
| - k. | Quality of the Midwives on conducting NVD. |  |  |  |
| - l. | Presence of 24/7 gynae & obs trained doctor in campus. |  |  |  |
| - m. | Presence of labour ward incharge SSN in campus. |  |  |  |
| - C. | Devloped OT Facility |  |  |  |
| - a. | Well equiped Gynae & Obs.OT |  |  |  |
| - b. | Infection control system |  |  |  |
| - c. | Presence of gynae & obs. Surgeon 24/7 in campus. |  |  |  |
| - d. | Presence of Anesthesiologist 24/7 in campus |  |  |  |
| - e. | Presnce of OT inchchargr SSN 24/7 in campus. |  |  |  |
| - f. | Emergency kitbox |  |  |  |
| - g. | Well equiped Post operative ward. |  |  |  |
| - 15. | Devolped paediatric health |  |  |  |
| - A. | Development in IMCI corner having the services(GOBI_FFF) |  |  |  |
| - a. | Asses the neutritional status. |  |  |  |
| - b. | Breast feeding. |  |  |  |
| - c. | Idea about oral rehydration therapy in dirrhoea. |  |  |  |
| - d. | Immunization of the baby. |  |  |  |
| - e. | Mother receving F.P method. |  |  |  |
| - d. | Treatnent of the disease. |  |  |  |
| - B. | Treatment in indoor having |  |  |  |
| - a. | Effective neonatal care facility. |  |  |  |
| - a.1 | Capable of neonatal I/V transfusion. |  |  |  |
| - a.2 | Capable of neonatal resuscitation. |  |  |  |
| - d.3 | Presence pedatrician 24/7 within campus. |  |  |  |
| - 16. | Devloped diagnostic Service |  |  |  |
| - a. | Functioning USG machine. |  |  |  |
| - b. | Functioning digital X-ray. |  |  |  |
| - c. | Functioning ECG machine |  |  |  |
| - e. | Functioning blood bank |  |  |  |
| - f. | Functioning lab. |  |  |  |
| - f.1. | Hematology |  |  |  |
| - f.2. | Biochemistry |  |  |  |
| - f.3 | Hormones |  |  |  |
| - f.4. | Pathology. |  |  |  |
| - 17. | Position in HSS score (Best= <100; Good= 101-200; Weak= >200) |  |  |  |
| - 18. | Power point Presentation &Video on UHC |  |  |  |
| - A. | Power Point Presentation having |  |  |  |
| - a. | Vision |  |  |  |
| - b. | Background history |  |  |  |
| - c | Health profile |  |  |  |
| - d. | Minimumlast 4 years major services performances. |  |  |  |
| - e. | SSK performance & progress. |  |  |  |
| - f. | Hospital services by photo. |  |  |  |
| - g. | Positve changes showing before after situtation by photo& phycal verification |  |  |  |
| - h. | Innvation activites |  |  |  |
| - i. | Acheivement/Recognations |  |  |  |
| - j. | Psitive information in media. |  |  |  |
| - k. | Challenges of the hospital. |  |  |  |
| - l. | Future plan(Waya forward) |  |  |  |
| - B | Video on UHC. |  |  |  |
| - a. | Duration -not morethan 4 minutes |  |  |  |
| - b. | Covers all major services. |  |  |  |
| - c. | Succes stoty |  |  |  |
| - d. | Comments of 2 patients, local Mp,Mayor,Civil Surgeon,UNO, UH&FPO |  |  |  |
| - 19. | Knowledge about 8th Five Year plan & SDG. |  |  |  |
| - a. | Orientatio on health related 8th 5 yr plan& SDG.(Targets & Goal) |  |  |  |
| - b. | Display in billboard. |  |  |  |
| - c. | Discimmation of idea that how the service provider can calculate |  |  |  |
| - d. | Display of yearly progress |  |  |  |
| - 20. | Zero-Tollarance on corruption |  |  |  |
| - a. | Discussion on moral based enveroment |  |  |  |
| - b. | Discussion on patients right. |  |  |  |
| - c. | Maintenance of morality. |  |  |  |
| - 21. | SSK |  |  |  |
| - A. | SSK Human Resourses |  |  |  |
| - a. | Ensureing the services of the guards |  |  |  |
| - b. | Ensureing the services of the cleaner |  |  |  |
| - B. | SSK Booth Functions. |  |  |  |

৯. মূল্যায়নের জন্য প্রশ্নমালা:

ক) উপজেলা স্বাস্থ্য কমপ্লেক্সের ক্ষেত্রে:

|  | উপজেলার নাম: |  |  |
| --- | --- | --- | --- |
|  | ক. ইউএইচএফপিও’র নাম: |  |  |
|  | খ. মোবাইল নং: |  |  |
|  | গ. ই-মেইল: |  |  |
|  | হাসপাতালের শয্যা সংখ্যা |  |  |
|  | উপজেলার তথ্য |  |  |
|  | ক. উপজেলার মোট জনসংখ্যা |  |  |
|  | খ. মোট গর্ভবতী মায়ের সংখ্যা |  |  |
|  | গ. মোট ০-১ বছরের শিশু সংখ্যা |  |  |
|  | ঘ. মোট ০-৫ বছরের শিশু সংখ্যা |  |  |
|  | মাসিক এইচএসএস নম্বরে সর্বশেষ অবস্থান |  |  |
|  | ক. সর্বনিম্ন: (বর্তমান বছরে) |  |  |
|  | খ. সর্বোচ্চ: (বর্তমান বছরে) |  |  |
|  | বায়োমেট্রিক হাজিরাঃ আগের মাসের (%) |  |  |
|  | ক. সর্বোচ্চ (বর্তমান বছরে) |  |  |
|  | খ. সর্বনিম্ন (বর্তমান বছরে) |  |  |
|  | মানবসম্পদ | পদ সংখ্যা | শুন্যপদ |
|  | ১.ক. চিকিৎসক |  |  |
|  | ১.খ. মেডিকেল অফিসার |  |  |
|  | ১.গ. মেডিকেল অফিসার (ওএসডি) |  |  |
|  | ১.ঘ. কনসালটেন্ট |  |  |
|  | ২. ক. নার্স |  |  |
|  | ২. খ. মিড-ওয়াইফ |  |  |
|  | ৩. পরিচ্ছন্ন কর্মী |  |  |
|  | ৪. ওয়ার্ড বয়/আয়া |  |  |
|  | মোট রোগীর সংখ্যা (আগের মাসের) |  |  |
|  | ক. অন্তঃবিভাগ |  |  |
|  | খ. জরুরী বিভাগ |  |  |
|  | গ. বহিঃবিভাগ |  |  |
|  | শয্যা ব্যবহারের হার (%) (আগের মাসের) |  |  |
|  | মোট গর্ভবতী পরিচর্যা (আগের মাসের) |  |  |
|  | ক. ১ম ভিজিট (সংখ্যা) |  |  |
|  | খ. চতুর্থ ভিজিট (সংখ্যা) |  |  |
|  | গ. মোট (সংখ্যা) |  |  |
|  | মোট প্রসব সংখ্যা (আগের মাসের) |  |  |
|  | ক. মোট স্বাভাবিক প্রসব |  |  |
|  | খ. মোট সিজারিয়ান প্রসব |  |  |
|  | গ. রাতে সিজারিয়ান প্রসব |  |  |
|  | মৃত জন্ম শিশুর সংখ্যা (আগের মাসের) |  |  |
|  | নবজাতক শিশু মৃত্যুর সংখ্যা (আগের মাসের) |  |  |
|  | হাসপাতালে মাতৃমৃত্যুর সংখ্যা (আগের মাসের) |  |  |
|  | মোট প্রসবোত্তর পরিচর্যা (আগের মাসের) |  |  |
|  | মেজর (বড়) অপারেশন (আগের মাসের) |  |  |
|  | ক. জেনারেল সার্জারি (সংখ্যা) |  |  |
|  | খ. গাইনি/অবস (সংখ্যা) |  |  |
|  | গ. ডেন্টাল অপারেশন (সংখ্যা) |  |  |
|  | ঘ. মোট মেজর অপারেশন (সংখ্যা) |  |  |
|  | ভায়া পরীক্ষার সংখ্যা (সর্বমোট) (আগের মাসের) |  |  |
|  | ক. পজিটিভ (সংখ্যা) |  |  |
|  | খ. নেগেটিভ (সংখ্যা) |  |  |
|  | সর্বক্ষণিক রক্ত পরিসঞ্চালন কার্যক্রম | হ্যাঁ | না |
|  | রোগ নির্ণয় ও পরীক্ষা-নিরীক্ষা (চালু কি না) |  |  |
|  | ১.ক. আল্ট্রাসনোগ্রাফি | হ্যাঁ | না |
|  | ১.খ. এক্স-রে | হ্যাঁ | না |
|  | ১.গ. ই.সি.জি | হ্যাঁ | না |
|  | ২. ক. সি.বি.সি | হ্যাঁ | না |
|  | ২.খ. বায়োকেমিস্ট্রি ও ইমিউনোলোজি | হ্যাঁ | না |
|  | ২.খ.১. লিপিড প্রোফাইল | হ্যাঁ | না |
|  | ২.খ.২. সেরাম ইলেক্ট্রোলাইট | হ্যাঁ | না |
|  | ২.খ.৩. সেরাম ক্রিয়েটিনিন | হ্যাঁ | না |
|  | ২.খ.৪. সেরাম ইউরিয়া | হ্যাঁ | না |
|  | ৩. ক. এইস.বি.এস. এ.জি | হ্যাঁ | না |
|  | ৩.খ. ব্লাড গ্লুকোজ | হ্যাঁ | না |
|  | ৩. গ. রক্তগ্রুপ ও স্ক্রিনিং | হ্যাঁ | না |
|  | চিকিৎসকদের আবাসিক (হাসপাতাল ক্যাম্পাসে) অবস্থান |  |  |
|  | ক. ইউএইচএফপিও | হ্যাঁ | না |
|  | খ. আবাসিক মেডিক্যাল অফিসার | হ্যাঁ | না |
|  | গ. কনসালটেন্ট, মেডিসিন | হ্যাঁ | না |
|  | ঘ. কনসালটেন্ট, সার্জারি | হ্যাঁ | না |
|  | ঙ. কনসালটেন্ট, এনেসথেসিয়া | হ্যাঁ | না |
|  | চ. কনসালটেন্ট, অবস গাইনি | হ্যাঁ | না |
|  | ছ. কনসালটেন্ট, শিশু স্বাস্থ্য | হ্যাঁ | না |
|  | নার্স/অন্যান্যদের আবাসিক অবস্থান |  |  |
|  | ক. নার্সিং সুপারভাইজার | হ্যাঁ | না |
|  | খ. ওটি সিস্টার | হ্যাঁ | না |
|  | গ. ইওসি সিস্টার | হ্যাঁ | না |
|  | ঘ. ইমার্জেন্সি ইন চার্জ | হ্যাঁ | না |
|  | ঙ. স্টোর ইন চার্জ | হ্যাঁ | না |
|  | চ. প্রধান অফিস সহকারি | হ্যাঁ | না |
|  | কমিউনিটি সহায়তা গ্রুপ গঠন | হ্যাঁ | না |
|  | কমিউনিটি হতে প্রাপ্ত সহযোগিতার পরিমাণ |  |  |
|  | ক. জনবল সহায়তা |  |  |
|  | খ. চিকিৎসা সামগ্রী সহায়তা |  |  |
|  | গ. আর্থিক সহায়তার পরিমাণ |  |  |
|  | মাসিক সভার সংখ্যা (আগের মাসের) |  |  |
|  | ক. স্বাস্থ্য সেবা উন্নয়ন কমিটি |  |  |
|  | খ. কমিউনিটি সহায়তা গ্রুপ |  |  |
|  | গ. সমন্বয় কমিটি |  |  |
|  | ঘ. কিউআইসি কমিটি |  |  |
|  | ঙ. ডাব্লুআইটি কমিটির সংখ্যা |  |  |
|  | চ. ডাব্লুআইটি কমিটির সভার সংখ্যা |  |  |
|  | ছ. ইওসি কমিটি |  |  |
|  | অভ্যর্থনা/তথ্য কেন্দ্র | হ্যাঁ | না |
|  | হাসপাতালের প্রবেশ পথে সাইকেল স্ট্যান্ড | হ্যাঁ | না |
|  | বহিঃবিভাগে রোগী পৃথকীকরণের ব্যবস্থা |  |  |
|  | ক. পুরুষ | হ্যাঁ | না |
|  | খ. নারী | হ্যাঁ | না |
|  | গ. শিশু | হ্যাঁ | না |
|  | ঘ. প্রসূতি ও গাইনি | হ্যাঁ | না |
|  | অন্তঃবিভাগে রোগী পৃথকীকরণের ব্যবস্থা |  |  |
|  | ক. পুরুষ | হ্যাঁ | না |
|  | খ. নারী | হ্যাঁ | না |
|  | গ. শিশু | হ্যাঁ | না |
|  | ঘ. প্রসূতি ও গাইনি | হ্যাঁ | না |
|  | বিষয়ভিত্তিক কর্নারের কার্যকারিতা |  |  |
|  | ক. এএনসি | হ্যাঁ | না |
|  | খ. পিএনসি | হ্যাঁ | না |
|  | গ. ভায়া | হ্যাঁ | না |
|  | ঘ. ইপিআই | হ্যাঁ | না |
|  | ঙ. এনসিডি | হ্যাঁ | না |
|  | চ. ইপিআই/মাতৃদুগ্ধ পান | হ্যাঁ | না |
|  | ছ. স্বাস্থ্য শিক্ষা | হ্যাঁ | না |
|  | দর্শনার্থী নিয়ন্ত্রণ কার্যক্রম | হ্যাঁ | না |
|  | রাত্রীকালীন ওয়ার্ড পরিদর্শন |  |  |
|  | ক. ইউএইচএফপিও | হ্যাঁ | না |
|  | খ. আবাসিক মেডিকেল অফিসার | হ্যাঁ | না |
|  | গ. নার্সিং সুপারভাইজার | হ্যাঁ | না |
|  | কনসালটেন্টদের রাত্রিকালীন ওয়ার্ড পরিদর্শন |  |  |
|  | ক. মেডিসিন | হ্যাঁ | না |
|  | খ. সার্জারি | হ্যাঁ | না |
|  | গ. গাইনি | হ্যাঁ | না |
|  | ঘ. শিশু | হ্যাঁ | না |
|  | রাত্রীকালীন জরুরী অপারেশন সুবিধা |  |  |
|  | ক. সাধারণ সার্জারি | হ্যাঁ | না |
|  | খ. ইওসি | হ্যাঁ | না |
|  | রোগীদের খাবার সরবরাহ তদারকি |  |  |
|  | ক. প্রতিদিন রোগীদের খাবার সামগ্রী কোনো কর্মকর্তা বুঝে নেন কি না? | হ্যাঁ | না |
|  | খ. রান্না করা রোগীর খাদ্য কর্মকর্তা পরীক্ষা করেন কি না? | হ্যাঁ | না |
|  | এম্বুলেন্স সার্ভিস |  |  |
|  | ক. সচল কি না | হ্যাঁ | না |
|  | খ. এম্বুলেন্স সার্ভিস থেকে আয় (আগের মাসের) |  |  |
|  | গ. এম্বুলেন্সের তেল বাবদ কত বাকি |  |  |
|  | বাৎসরিক মোট মৃত্যুর সংখ্যা |  |  |
|  | মাসিক মৃত্যু পর্যালোচনা | হ্যাঁ | না |
|  | পৌরসভায় বাৎসরিক কর প্রদানের পরিমাণ |  |  |
|  | বাৎসরিক মোট রাজস্ব্য আয় |  |  |

| বছর | ইমার্জেন্সি | আউটডোর | ইনডোর | ইওসি ভর্তি | শয্যা ব্যবহারের হার (%) |
| --- | --- | --- | --- | --- | --- |
| ২০১৮ |  |  |  |  |  |
| ২০১৯ |  |  |  |  |  |
| ২০২০ |  |  |  |  |  |
| ২০২১ |  |  |  |  |  |
| ২০২২ |  |  |  |  |  |

নিরাপদ মাতৃত্বসেবা

| বছর | গর্ভবতী সংক্রান্ত ১ম ভিজিট | গর্ভবতী সংক্রান্ত ৪র্থ ভিজিট | সর্বমোট ডেলিভারি | ডেলিভারি |  | পিএনসি |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | নরমাল | সিজার | পিএনসি ১ম | সর্বমোট ডেলিভারি |
| ২০১৮ |  |  |  |  |  |  |  |
| ২০১৯ |  |  |  |  |  |  |  |
| ২০২০ |  |  |  |  |  |  |  |
| ২০২১ |  |  |  |  |  |  |  |
| ২০২২ |  |  |  |  |  |  |  |

খ) জেলা হাসপাতালের ক্ষেত্রে:

|  | জেলার নাম: |  |  |
| --- | --- | --- | --- |
|  | ক. তত্ত্বাবধায়কের নাম: |  |  |
|  | খ. মোবাইল নং: |  |  |
|  | গ. ই-মেইল: |  |  |
|  | জেলা হাসপাতালের শয্যা সংখ্যা |  |  |
|  | জেলার তথ্য |  |  |
|  | ক. জেলার মোট জনসংখ্যা |  |  |
|  | খ. মোট গর্ভবতী মায়ের সংখ্যা |  |  |
|  | গ. মোট ০-১ বছরের শিশু সংখ্যা |  |  |
|  | ঘ. মোট ০-৫ বছরের শিশু সংখ্যা |  |  |
|  | মাসিক এইচএসএস নম্বরে অবস্থান |  |  |
|  | ক. সর্বনিম্ন: (বর্তমান বছরে) |  |  |
|  | খ. সর্বোচ্চ: (বর্তমান বছরে) |  |  |
|  | বায়োমেট্রিক হাজিরাঃ আগের মাসের (%) |  |  |
|  | ক.সর্বোচ্চ (বর্তমান বছরে) |  |  |
|  | খ.সর্বনিম্ন (বর্তমান বছরে) |  |  |
|  | মানবসম্পদ | পদ সংখ্যা | শুন্যপদ |
|  | ১.ক. চিকিৎসকঃ |  |  |
|  | ১.খ. মেডিকেল অফিসার |  |  |
|  | ১.গ. মেডিকেল অফিসার (ওএসডি) |  |  |
|  | ১.ঘ. কনসালটেন্ট |  |  |
|  | ২. ক. নার্স |  |  |
|  | ২. খ. মিড-ওয়াইফ |  |  |
|  | ৩. পরিচ্ছন্ন কর্মী |  |  |
|  | ৪. ওয়ার্ড বয়/আয়া |  |  |
|  | মোট রোগীর সংখ্যা (আগের মাসের) |  |  |
|  | ক. অন্তঃবিভাগ |  |  |
|  | খ. জরুরী বিভাগ |  |  |
|  | গ. বহিঃবিভাগ |  |  |
|  | শয্যা ব্যবহারের হার (%) (আগের মাসের) |  |  |
|  | মোট গর্ভবতী পরিচর্যা (আগের মাসের) |  |  |
|  | ক. ১ম ভিজিট (সংখ্যা) |  |  |
|  | খ. চতুর্থ ভিজিট (সংখ্যা) |  |  |
|  | গ. মোট (সংখ্যা) |  |  |
|  | মোট প্রসব সংখ্যা (আগের মাসের) |  |  |
|  | ক. মোট স্বাভাবিক প্রসব |  |  |
|  | খ. মোট সিজারিয়ান প্রসব |  |  |
|  | গ. রাতে সিজারিয়ান প্রসব |  |  |
|  | মৃত জন্ম শিশুর সংখ্যা (আগের মাসের) |  |  |
|  | নবজাতক শিশু মৃত্যুর সংখ্যা (আগের মাসের) |  |  |
|  | হাসপাতালে মাতৃমৃত্যুর সংখ্যা (আগের মাসের) |  |  |
|  | মোট প্রসবোত্তর পরিচর্যা (আগের মাসের) |  |  |
|  | মেজর (বড়) অপারেশন (আগের মাসের) |  |  |
|  | ক. জেনারেল সার্জারি (সংখ্যা) |  |  |
|  | খ. গাইনি/অবস (সংখ্যা) |  |  |
|  | গ. অর্থোপেডিক (সংখ্যা) |  |  |
|  | ঘ. নাক-কান-গলা অপারেশন (সংখ্যা) |  |  |
|  | ঙ. চক্ষু অপারেশন (সংখ্যা) |  |  |
|  | চ. ডেন্টাল অপারেশন (সংখ্যা) |  |  |
|  | ছ. মোট মেজর অপারেশন (সংখ্যা) |  |  |
|  | সার্বক্ষণিক রক্ত পরিসঞ্চালন কার্যক্রম | হ্যাঁ | না |
|  | রোগ নির্ণয় ও পরীক্ষা-নিরীক্ষা (চালু কি না) |  |  |
|  | ১.ক. আল্ট্রাসনোগ্রাফি | হ্যাঁ | না |
|  | ১.খ. এক্স-রে | হ্যাঁ | না |
|  | ১.গ. ই.সি.জি | হ্যাঁ | না |
|  | ২.ক. সি.বি.সি | হ্যাঁ | না |
|  | ২.খ. বায়োকেমিস্ট্রি ও ইমিউনোলোজি | হ্যাঁ | না |
|  | ২.খ.১. লিপিড প্রোফাইল | হ্যাঁ | না |
|  | ২.খ.২. সেরাম ইলেক্ট্রোলাইট | হ্যাঁ | না |
|  | ২.খ.৩. সেরাম ক্রিয়েটিনিন | হ্যাঁ | না |
|  | ২.খ.৪. সেরাম ইউরিয়া | হ্যাঁ | না |
|  | ৩.ক. এইস.বি.এস. এ.জি | হ্যাঁ | না |
|  | ৩.খ. ব্লাড গ্লুকোজ | হ্যাঁ | না |
|  | ৩. গ. রক্তগ্রুপ ও স্ক্রিনিং | হ্যাঁ | না |
|  | চিকিৎসকদের আবাসিক (হাসপাতাল ক্যাম্পাসে) অবস্থান |  |  |
|  | ক. তত্ত্বাধা্য়ক | হ্যাঁ | না |
|  | খ. আবাসিক মেডিক্যাল অফিসার | হ্যাঁ | না |
|  | গ. কনসালটেন্ট, মেডিসিন | হ্যাঁ | না |
|  | ঘ. কনসালটেন্ট, সার্জারি | হ্যাঁ | না |
|  | ঙ. কনসালটেন্ট, এনেসথেসিয়া | হ্যাঁ | না |
|  | চ. কনসালটেন্ট, অবস গাইনি | হ্যাঁ | না |
|  | ছ. কনসালটেন্ট, অর্থোপেডিকস | হ্যাঁ | না |
|  | জ. কনসালটেন্ট, কার্ডিওলজি | হ্যাঁ | না |
|  | ঝ. কনসালটেন্ট, শিশু স্বাস্থ্য | হ্যাঁ | না |
|  | ঞ. কনসালটেন্ট, নাক,কান, গলা | হ্যাঁ | না |
|  | ট. কনসালটেন্ট চক্ষু | হ্যাঁ | না |
|  | নার্স/অন্যান্যদের আবাসিক অবস্থান |  |  |
|  | ক. নার্সিং সুপার | হ্যাঁ | না |
|  | খ. ওটি সিস্টার | হ্যাঁ | না |
|  | গ. ইওসি সিস্টার | হ্যাঁ | না |
|  | ঘ. ইমার্জেন্সি ইন চার্জ | হ্যাঁ | না |
|  | ঙ. স্টোর ইন চার্জ | হ্যাঁ | না |
|  | চ. প্রধান অফিস সহকারি | হ্যাঁ | না |
|  | কমিউনিটি সহায়তা গ্রুপ গঠন | হ্যাঁ | না |
|  | কমিউনিটি হতে প্রাপ্ত সহযোগিতা |  |  |
|  | ক. জনবল সহায়তা |  |  |
|  | খ. চিকিৎসা সামগ্রী সহায়তা |  |  |
|  | গ. আর্থিক সহায়তার পরিমাণ |  |  |
|  | মাসিক সভার সংখ্যা (আগের মাসের) |  |  |
|  | ক. স্বাস্থ্য সেবা উন্নয়ন কমিটি |  |  |
|  | খ. কমিউনিটি সহায়তা কমিটি |  |  |
|  | গ. সমন্বয় কমিটি |  |  |
|  | ঘ. কিউআইসি কমিটি |  |  |
|  | ঙ. ডাব্লুআইটি কমিটি (প্রতি সপ্তাহে সভার সংখ্যা) |  |  |
|  | অভ্যর্থনা/তথ্য কেন্দ্র | হ্যাঁ | না |
|  | হাসপাতালের প্রবেশ পথে সাইকেল স্ট্যান্ড | হ্যাঁ | না |
|  | বিষয়ভিত্তিক কর্নারের কার্যকারিতা |  |  |
|  | ক. এএনসি | হ্যাঁ | না |
|  | খ. পিএনসি | হ্যাঁ | না |
|  | গ. ভায়া | হ্যাঁ | না |
|  | ঘ. ইপিআই | হ্যাঁ | না |
|  | ঙ. এনসিডি | হ্যাঁ | না |
|  | চ. মাতৃদুগ্ধ পান | হ্যাঁ | না |
|  | ছ. স্বাস্থ্য শিক্ষা | হ্যাঁ | না |
|  | দর্শনার্থী নিয়ন্ত্রণ কার্যক্রম | হ্যাঁ | না |
|  | রাত্রীকালীন ওয়ার্ড পরিদর্শনঃ |  |  |
|  | ক. তত্ত্বাবধায়ক নার্সিং | হ্যাঁ | না |
|  | খ. আবাসিক মেডিকেল অফিসার | হ্যাঁ | না |
|  | গ. নার্সিং সুপার | হ্যাঁ | না |
|  | কনসালটেন্টদের রাত্রিকালীন ওয়ার্ড পরিদর্শন |  |  |
|  | ক. মেডিসিন | হ্যাঁ | না |
|  | খ. সার্জারি | হ্যাঁ | না |
|  | গ. গাইনি | হ্যাঁ | না |
|  | ঘ. ইএনটি | হ্যাঁ | না |
|  | ঙ. অর্থোপেডিকস | হ্যাঁ | না |
|  | চ. চক্ষু | হ্যাঁ | না |
|  | ছ. কার্ডিওলজি | হ্যাঁ | না |
|  | জ. শিশু | হ্যাঁ | না |
|  | রাত্রীকালীন জরুরী অপারেশন সুবিধা |  |  |
|  | ক. সাধারণ সার্জারি | হ্যাঁ | না |
|  | খ. ইওসি | হ্যাঁ | না |
|  | গ. অর্থোপেডিক | হ্যাঁ | না |
|  | ঘ. চক্ষু | হ্যাঁ | না |
|  | ঙ. নাক-কান-গলা | হ্যাঁ | না |
|  | রোগীদের খাবার সরবরাহ তদারকি: ক) প্রতিদিন রোগীদের খাবার সামগ্রী কোনো কর্মকর্তা বুঝে নেন কিনা? | হ্যাঁ | না |
|  | খ)রান্না করা রোগীর খাদ্য কর্মকর্তা পরীক্ষা করেন কিনা? | হ্যাঁ | না |
|  | বাৎসরিক মোট রাজস্ব্য আয় |  |  |
|  | বাৎসরিক মোট মৃত্যুর সংখ্যা |  |  |
|  | মাসিক মৃত্যু পর্যালোচনা | হ্যাঁ | না |
|  | এম্বুলেন্স সার্ভিস |  |  |
|  | ক. সচল কি না | হ্যাঁ | না |
|  | খ. এম্বুলেন্স সার্ভিস থেকে আয় (আগের মাসের) |  |  |
|  | গ. এম্বুলেন্সের তেল বাবদ কত বাকি |  |  |

| বছর | ইমার্জেন্সি | আউটডোর | ইনডোর | ইওসি ভর্তি | শয্যা ব্যবহারের হার (%) |
| --- | --- | --- | --- | --- | --- |
| ২০১৮ |  |  |  |  |  |
| ২০১৯ |  |  |  |  |  |
| ২০২০ |  |  |  |  |  |
| ২০২১ |  |  |  |  |  |
| ২০২২ |  |  |  |  |  |

নিরাপদ মাতৃত্বসেবা

| বছর | গর্ভবতী সংক্রান্ত ১ম ভিজিট | গর্ভবতী সংক্রান্ত ৪র্থ ভিজিট | সর্বমোট ডেলিভারি | ডেলিভারি |  | পিএনসি |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | নরমাল | সিজার | পিএনসি ১ম | সর্বমোট ডেলিভারি |
| ২০১৮ |  |  |  |  |  |  |  |
| ২০১৯ |  |  |  |  |  |  |  |
| ২০২০ |  |  |  |  |  |  |  |
| ২০২১ |  |  |  |  |  |  |  |
| ২০২২ |  |  |  |  |  |  |  |

জেলা-উপজেলায় চৌগাছা-ঝিনাইদহের আদর্শে স্বাস্থ্য ব্যবস্থাপনা সম্প্রসারণ:

SOP Number: 1

SOP Title: প্রাথমিক মূল্যায়ন প্রতিবেদন

উদ্দেশ্য: হাসপাতালের সার্বিক কার্যক্রমের বর্তমান অবস্থা অর্থাৎ সরকারি সম্পদ ব্যবহার এবং বিভিন্ন সেবার গুণ ও পরিমাণগত অবস্থা নির্ণয় করে একটি মূল্যায়ন প্রতিবেদন তৈরী করা

কর্মক্ষেত্রসমূহ:

- প্রতিষ্ঠানের সংক্ষিপ্ত ইতিহাস

- হাসপাতালের পরিষ্কার-পরিচ্ছন্নতা

- নিরাপত্তা ও কর্মপরিবেশ

- রোগ সংক্রমণ নিয়ন্ত্রণ

- আর্থিক ব্যবস্থাপনা

- ঔষধ, যন্ত্রপাতি ও সরঞ্জামাদি

- বিভিন্ন বিভাগের কার্যক্রমের অবস্থা

- কোন পুরস্কার বা প্রশংসা অর্জন

দায়িত্বসমূহ:

তত্ত্বাবধায়ক ও আবাসিক মেডিকেল অফিসারসহ বিভিন্ন ইউনিট প্রধানগণ

কার্যপদ্ধতি:

নির্ধারিত ফরম্যাট প্রস্তুতকরণ।

SOP Number: ২

SOP Title: সমস্যাসমূহ চিহ্নিতকরণ

উদ্দেশ্য:

- প্রতিষ্ঠানের সকল সমস্যা চিহ্নিতকরণের মাধ্যমে সমাধানের প্রাথমিক পথসমূহ বের করা

- প্রতিষ্ঠানটির সকল সম্পদ ব্যবহার করে সার্বিক উন্নতিতে ভূমিকা রাখা

কর্মপদ্ধতি:

- সকল কর্মকর্তা-কর্মচারীদেরকে সমস্যা চিহ্নিতকরণের তাগিদ দেয়া এবং নির্দিষ্ট সময়ের মধ্যে জমা দেয়া

- সকল সমস্যাসমূহ একত্রিত করে বিভিন্ন ধরণের সমস্যাগুলোর শ্রেণীবিভাগ করা: ছোট, মাঝারী ও বড় সমস্যা

- প্রতি সপ্তাহে WIT কমিটির মাধ্যমে নতুন সমস্যা চিহ্নিত করা ও সমাধানের অগ্রগতির মূল্যায়ন করা

দায়িত্বসমূহ:

- QIC ও WIT কমিটি

- তত্ত্বাবধায়ক/ইউএইচএফপিও ও আবাসিক মেডিকেল অফিসারসহ বিভিন্ন ইউনিট প্রধানগণ

SOP Number: ৩

SOP Title: লক্ষ্যমাত্রা (Target) নির্ধারণ করা

উদ্দেশ্য:

- লক্ষ্যবস্তু (Target) সমূহ সম্পর্কে তার কর্মকর্তা ও কর্মচারীদের মধ্যে স্বচ্ছ ধারণা সৃষ্টি করা

- সরকারী কার্যক্রম সফলভাবে বাস্তবায়নের পরিকল্পনা করা

- লক্ষ্যবস্তু বাস্তবায়নের মূল্যায়নের মাধ্যমে তথ্যভিত্তিক দায়বদ্ধতা সৃষ্টি করা

কর্মপদ্ধতি:

লক্ষ্য ও লক্ষ্যমাত্রা

- ২০২৩ সাল নাগাদ সপ্তম পঞ্চবার্ষিকী পরিকল্পনায় স্বাস্থ্য, পুষ্টি ও জনসংখ্যা সংক্রান্ত লক্ষ্য ও লক্ষ্যবস্তু সম্পর্কে স্থানীয় প্রতিষ্ঠানের অবস্থার তথ্য সংগ্রহ এবং সংশ্লিষ্ট নির্ণায়কের (indicator) মাধ্যমে মূল্যায়ন করা

- মাসিক, ত্রৈমাসিক, ষান্মাসিক ও বার্ষিক হিসিএবে এইসকল লক্ষ্যমাত্রার অগ্রগতির মূল্যায়ন করা

- অগ্রগতিসমূহ কেন্দ্রীয়ভাবে ও সংশ্লিষ্ট বিভাগে প্রদর্শনী করা

- নতুন নতুন পদ্ধতি উদ্ভাবনের মাধ্যমে লক্ষ্য বাস্তবায়নের প্রক্রিয়াকে উৎসাহিত করা এবং তাকে বিশেষ গুরুত্ব দেয়া

দায়িত্ব:

- তত্ত্বাবধায়ক/ইউএইচএফপিও ও আবাসিক মেডিকেল অফিসারসহ বিভিন্ন ইউনিট প্রধানগণ

- কমিউনিটি সহায়তা গ্রুপের সদস্যবৃন্দ

SOP Number: 4

SOP Title:	jÿ¨mg~n ev¯Íevq‡b †mev`vbKvix‡`i Aw½Kvi AR©b Kiv

D‡Ïk¨:

- ¯^”QZv I Revew`wnZvi gva¨‡g †mev `vbKvix I MÖnxZvi gv‡S cvi¯úwiK Av¯’v m„wó Kiv

- ¯’vbxq RbcÖwZwbwa, cÖkvmb I miKvix Kg©KZ©v, mvsevw`K, wkÿK mn mgv‡Ri wewkóe¨w³e‡M©i mv‡_ Av‡jvPbv K‡i miKvix Kg©m~wP ev¯Íevq‡bi Aw½Kvi Kiv‡bv

- ‡mev`vbKvix‡`i Kvh©µ‡g RbevÜe `„wófw½ AR©b Kiv I RbgÛjxi (Community) mnvqZvi ¸iæZ¡ I cÖ‡qvRbxqZv eywS‡q Aw½Kvi Av`vq Kiv

Kg©c×wZ:

- wewkó e¨w³e‡M©i mv‡_ m¤¢e n‡j e¨w³MZ ch©v‡q, Ab¨_vq `je×fv‡e gZwewbgq Kiv

- wewfbœ †kÖYx-‡ckvi cÖwZwbwai mv‡_ gZ wewbgq Kiv

- wewfbœ miKvix wefv‡Mi mv‡_, we‡kl K‡i Awdmvm© K¬v‡ei m`m¨‡`i mv‡_ gZwewbgq Kiv

- ‡mev`vbKvix‡`i mv‡_ e¨w³MZ I MÖæc ch©v‡q jÿ¨, D‡Ïk¨ wb‡q Av‡jvPbv Kiv Ges Zv‡`i gZvgZ †bqv

`vwqZ¡:

- ZË¡veavqK/BDGBPGdwcI I AvevwmK †gwWK¨vj Awdmvi mn wewfbœ BDwbU cÖavbMY

- KwgDwbwU mnvqZv MÖæ‡ci m`m¨e„›`

SOP Number: 5

SOP Title:	g~j¨‡eva wfwËK Kg©cwi‡ek I cÖvwZôvwbK ms¯‹…wZ M‡o †Zvjv

D‡Ïk¨:

- nvmcvZvj‡K GKwU cweÎ ¯’vb wn‡m‡e we‡ePbv Kiv Ges Gi cweÎZv msiÿY Ki‡Z DØy× Kiv

- ÓKg Li‡P Kvh©Ki †mevÓ G g~j¨‡ev‡ai Ici wfwË K‡i cÖwZwU Kvh©µg cwiPvjbv Kiv

- ‡mev`vbKvixMY KZ…©K †ivMx‡`i‡K ¯^Rb wn‡m‡e we‡ePbv I Zv‡`i Amy¯’Zv‡K ms‡e`bkxjfv‡e e¨e¯’vcbv Kiv

- ‡Kvbµ‡gB `ybx©wZi mv‡_ Av‡cvl bv Kiv

Kg©c×wZ:

- miKvix wbqg-Kvbyb h_vh_fv‡e Rvbv‡bv I †g‡b Pj‡Z mnvqZv Kiv

- mgqvbyeZx©Zv, cvi¯úwiK kÖ×v‡eva, `vwqZ¡kxjZv Ggbfv‡e cÖ`k©b Kiv †hb cÖwZwU Kg©KZ©v I Kg©Pvix GKwU Avb›`Nb cwi‡e‡k Ae¯’vb K‡ib

- Kg©KZ©v I Kg©Pvix‡`i‡K Zv‡`i ˆbwZKZv m¤ú‡K© m‡PZb Kiv

- cÖwZôv‡bi feb I cÖv½‡b gbxlx‡`i gvbe †mev msµvšÍ evYx cÖ`k©b Kiv

- ‡ivMx‡`i KvQ †_‡K Ówgwó LvIqvÓ ev Ómš‘wóÓi bvg K‡i A_© Av`vq‡K k~b¨ mnbkxjZv cÖ`k©b Kiv

`vwqZ¡:

- ZË¡veavqK/BDGBPGdwcI I AvevwmK †gwWK¨vj Awdmvi mn wewfbœ BDwbU cÖavbMY

- KwgDwbwU mnvqZv MÖæ‡ci m`m¨e„›`

SOP Number: 6

SOP Title: jÿ¨ (Goal) ev¯Íevq‡b mvgvwRK Av‡›`vjb M‡o †Zvjv

D‡Ïk¨:

- miKv‡ii mßg cÂ evwl©Kx cwiKíbv I me©Rbxb ¯^v¯’¨ myiÿv ev¯Íevq‡b RbMY‡K m¤ú„³ Kiv‡K GKwU Acwinvh© Dcv`vb wn‡m‡e wPwýZ Kiv

- miKvix mÿgZv‡K Av‡iv Kvh©Ki fv‡e Kv‡R jvMv‡bvi Rb¨ Z_¨wfwËK m‡PZbZv M‡o †Zvjv

Kg©c×wZ:

- RbcÖwZwbwa, ¯’vbxq cÖkvmb, miKvix Kg©KZ©v, mvsevw`K I wewfbœ †kÖYx-‡ckvi cÖwZwbwa‡`i‡K e¨w³MZ †hvMv‡hvM I MÖæc wfwËK Av‡jvPbv K‡i DØy× Kiv

- ¯^v¯’¨ msjvc Pvjy Kiv

- `vwqZ¡kxj e¨w³‡`i wb‡q GKwU Qvqv KwgwU MVb Kiv

`vwqZ¡:

- ZË¡veavqK/BDGBPGdwcI I AvevwmK †gwWK¨vj Awdmvi mn wewfbœ BDwbU cÖavbMY

- KwgDwbwU mnvqZv MÖæ‡ci m`m¨e„›`

SOP Number: 7

SOP Title: gvbm¤úbœ †mev`vb ev¯Íevq‡b 5Gm KvB‡Rb c×wZ ev¯Íevqb Kiv

D‡Ïk¨:

- gvbm¤úbœ ¯^v¯’¨‡mev `v‡b cÖv_wgK Kvh©µg wn‡m‡e 5Gm Kvh©µg ïiæ K‡i ¯^v¯’¨‡mev cwi‡ek ˆZix Kiv

- miKvix m¤ú‡`i m‡e©v”P e¨envi wbwðZ Kiv

- ¯^v¯’¨‡mev `vbKvix‡`i‡K mgm¨v wPwýZKiY, AMÖvwaKvi wba©viY I mgvav‡bi AMÖMwZ cwigv‡c cÖwkwÿZ Kiv

Kg©c×wZ:

- ‡mev`vbKix‡`i 5Gm KvB‡Rb m¤ú‡K© cÖwkÿY †`qv

- wewfbœ IqvW©/BDwb‡U WIT MVb Kiv

- ZË¡veavqK/BDGBPGdwcIÕi †bZ„‡Z¡ QIC MVb Kiv Ges GKRb †dvKvj e¨w³ wba©viY Kiv

- Kaizen/PDCA c×wZ m¤ú‡K© aviYv †`qv

`vwqZ¡:

- ZË¡veavqK/BDGBPGdwcI I AvevwmK †gwWK¨vj Awdmvi, †dvKvj e¨w³

SOP Number: 8

SOP Title: wbivc` i³ mÂvjb Kvh©µg

D‡Ïk¨:

- Riæix cÖ‡qvR‡b †ivMx‡`i wbivc` i³ mieiv‡ni e¨e¯’v Kiv

- `ªæZZg mg‡q i³ mieivn Kiv

- i³`vZv‡`i GKwU `j MVb K‡i GKwU Pjgvb i³ e¨vsK MVb Kiv

Kg©c×wZ:

- wbivc` i³ mÂvj‡bi Rb¨ GKwU Kÿ wba©vwiZ Kiv I cÖ‡qvRbxq Avmevec‡Îi e¨e¯’v Kiv

- ‡¯^”Qv i³`vbKvix‡`i †gvevBj †dvb b¤^i mn GKwU ZvwjKv cÖ`k©b Kiv

- ZvwjKv‡Z 200-500 (Kgc‡ÿ) R‡bi GKwU ZvwjKv cÖ¯‘Z Kiv

- `vZv‡`i i³ wbivc` wKbv Zv cixÿv mnRjf¨ Kiv

- i³ e¨vs‡Ki †hvMv‡hvM mve©ÿwYK (24/7) mPj ivLv

- ¸iæZ¡c~Y© RvZxq w`em¸‡jv‡Z i³`vZv msMÖ‡n mgv‡Ri wewkó Rb‡`I AskMÖnY NUv‡bv

- el©‡k‡l i³`vZv‡`i DrmvwnZ Kivi j‡ÿ¨ m¤^a:bv †`qv

- Mfxi iv‡Î i³`vZv‡`i †hvMv‡hv‡Mi `vwqZ¡ cvjb Kivi Rb¨ GKwU we‡kl `j MVb Kiv

`vwqZ¡ mg~n:

- ‡mev`vbKvix‡`i‡K i³`v‡bi ¸iæZ¡ eywS‡q ejv

- RbMY‡K m¤ú„³ K‡i i³`vbKvixi msL¨v evov‡bv

- Mf©eZx gv‡q‡`i i³ MÖæc mbv³ K‡i Zv‡`i cÖ‡Z¨‡Ki Rb¨ GKB MÖæ‡ci `yÕRb m¤¢ve¨ i³`vZvi †gvevBj b¤^i mn Z_¨ gv‡qi Kv‡Q ivLv

ev¯ÍevqbKvix

- ZË¡veavqK/BDGBPGdwcI I AvevwmK †gwWK¨vj Awdmvimn GKwU DcKwgwU MVb Kiv

- G msµvšÍ WIT m`m¨e„›`

- wba©vwiZ mgq ci ci Gi AMÖMwZ ch©v‡jvPbv Kiv

SOP Number: 9

SOP Title:	 AvBGgwmAvB Kb©vi Kvh©µg

D‡Ïk¨:

- ewntwefv‡M AvMZ mKj wkïi wPwKrmv cÖ`vb I cÖwZ‡iva ¯^v¯’¨ m¤ú‡K© m‡PZb Kiv Ges RwUj †ivMx †idvi Kiv

- wewfbœ ‡mev DcKiY e¨env‡ii gva¨‡g Kb©vi‡K AvKl©Yxq I wek¦vm‡hvM¨ Kiv

- AvMZ †ivMx‡`i mš‘wó AR©b Kiv

Kg©c×wZ:

- AvBGgwmAvB-Gi Rb¨ GKwU Kÿ wba©viY Kiv

- GKRb †gwWK¨vj Gwm÷¨v›U‡K `vwqZ¡ †`qv

- cÖ‡qvRbxq cwigv‡Y ¯^v¯’¨ wkÿv DcKiY msMÖn Kiv

- wkï‡`i GOBI-FFF (Maintenance of growth chart, oral rehydration therapy, breast feeding, immunization, family planning, food fortification, female education) m¤ú‡K© gv‡q‡`i aviYv †`qv

`vwqZ¡mg~n:

- ‡mev`vbKvix‡`‡K Gi D‡Ïk¨ m¤ú‡K© AewnZ Kiv

- RbMY‡K Kb©v‡ii ¸iæZ¡ †evSv‡bv

ev¯ÍevqbKvix

- ZË¡veavqK/BDGBPGdwcI, AviGgI

- WIT Gi mKj m`m¨ KZ…©K mg‡q mg‡q Kv‡Ri AMÖMwZ ch©v‡jvPbv

SOP Number: 9

SOP Title:	 cÖm~wZ †mev (GGbwm) Kvh©µg

D‡Ïk¨:

- Mf©Kv‡j gv‡q‡`i I Mf©¯’ wkï‡`i my¯’ ivL‡Z mvnvh¨ Kiv

- SzuwKc~Y© gv‡q‡`i wPwýZ Kiv

- cÖvwZôvwbK cÖm‡e DrmvwnZ Kiv

- miKvix nvmcvZvj‡K Ggbfv‡e RbevÜe K‡i M‡o †Zvjv †hb gv‡qiv GLv‡b cÖme †mev wb‡Z ¯^v”Q›`¨ †eva K‡ib

- Mf©Kvjxb cwiPh©v, cÖm~wZ I wkï †mev GKB cÖwZôv‡b †`qvi Rb¨ cÖwZôvb‡K cÖ¯‘Z ivLv

Kg©c×wZ:

- Mf©eZx gv‡q‡`i cwiPh©vi Rb¨ AvmevecÎ mn GKwU fv‡jv K‡ÿi e¨e¯’v Kiv

- GKRb `ÿ avÎx (wgWIqvBd)‡K `vwqZ&¦ †`qv (wbeÜb mn cÖv_wgK cixÿv wbixÿvi Rb¨)

- cÖm~wZ gv I Zv‡`i mw½‡`i c„_K ¯^v¯’¨ wkÿv Kb©v‡i AwWI-wfmyqvj c×wZ‡Z ¯^v¯’¨ wkÿvi e¨e¯’v Kiv

- Mf©Kv‡j Kgc‡ÿ cvuP evi (Mf©mg‡qi 1-12 mßvn, 15-20 mßvn, 24-28 mßvn, 31-32 mßvn, 36Zg mßvn) ¯^v¯’¨ cÖwZôvb †_‡K Mf©Kvjxb ‡mev †bqv

- gv‡q‡`i G msµvšÍ mKj cixÿvi e¨e¯’v ivLv

- cÖwZwU Mf©eZx gv‡K AwfÁ ‡gwWK¨vj Awdmvi Øviv wPwKrmv wbwðZ Kiv

- gv‡q‡`i e¨w³MZ †MvcbxqZv iÿvq cÖ‡qvRbxq e¨e¯’v †bqv

- ‡mevMÖnxZv‡`i A‡cÿv Kivi mgq †hb b~¨bZg nq, †mfv‡e †mev Kvh©µg msMwVZ Kiv

- ‡mev`vbKvix‡`i `„wófw½ I AvPiY RbevÜe Kiv

`vwqZ¡mg~n:

- Rbm‡PZbZv evov‡bv

- ‡mev`vbKvix‡`i Gi ¸iæZ¡ m¤ú‡K© Abyaveb Kiv

ev¯ÍevqbKvix

- ZË¡veavqK/BDGBPGdwcI I AvevwmK †gwWK¨vj Awdmvi

- WIT Gi mKj m`m¨ KZ…©K Kvh©µ‡gi cwiKíbv I mg‡q mg‡q Kv‡Ri AMÖMwZ ch©v‡jvPbv

SOP Number: 10

SOP Title:	¯^v¯’¨ wkÿv Kvh©µg

D‡Ïk¨:

- RbMY‡K ¯^v¯’¨ m‡PZb Kiv

- ‡mevMÖnxZv‡`i AvPiY cwieZ©b

- mswkøó ¯^v¯’¨ cÖwZôv‡b cÖ‡`q †mevmg~n m¤ú‡K© RbMY‡K AewnZ Kiv I G my‡hvM e¨env‡i DrmvwnZ Kiv

- ‡mev`vbKvix I MÖnxZv‡`i g‡a¨ eÜzZ¡c~Y© m¤úK© M‡o †Zvjv I Z_¨ Av`vb-cÖ`vb Kiv

- RbM‡Yi ¯^v¯’¨ m¤úwK©Z mycvwik MÖnY Kiv

Kg©c×wZ:

- ¯^v¯’¨ wkÿvi Rb¨ ¯’vb wbe©vPb Kiv

- emvi fvj e¨e¯’v Kiv

- ¸iæZ¡c~Y© †mev¸‡jv †cv÷vi I AwWI-wfmyqvj c×wZi gva¨‡g Dc¯’vcb Kiv

- welq Abyhvqx mvßvwnK †iv÷vi I †m Abyhvqx `vwqZ¡ e›Ub Kiv

- ¯^v¯’¨ wkÿv Kvh©µ‡g `vwqZ¡kxj‡`i mswkøó Kiv

- hviv ¯^v¯’¨ wkÿv †`‡eb Zv‡`i‡K cÖwkÿZ Kiv

- ¯^v¯’¨ wkÿv msµvšÍ †iKW©mg~n msiÿY Kiv

`vwqZ¡:

- ZË¡veavqK/BDGBPGdwcI I AvevwmK †gwWK¨vj Awdmvi Ab¨vb¨ †gwWK¨vj Awdmvi mn `vwqZ¡kxj e¨w³eM© ¯^v¯’¨ wkÿv cwiPvjbv Ki‡eb

- KwgDwbwU mnvqZv MÖæ‡ci m`m¨e„›` ¯^v¯’¨ wkÿvq Ask †b‡eb

- KvDwÝwjsGi e¨vcv‡i RbMY‡K DrmvwnZ Ki‡eb

- ¯^v¯’¨ wkÿvi e¨vcv‡i ‡mev`vbKvix‡`i `„wófw½/AvPiY cwieZ©b Ki‡Z n‡e

ev¯ÍevqbKvix

- BDGBPGdwcI, AviGgI mn mKj Awdmvie„›`

SOP Number: 11

SOP Title:	 Kvh©µ‡gi Z_¨vewj cÖ`k©b

D‡Ïk¨:

- RbMY‡K ¯^v¯’¨ cÖwZôv‡bi we`¨gvb †mevmg~n m¤ú‡K© AewnZ Kiv

- ‡Kvb& †Kvb& †mev †Kv_vq cvIqv hvq, Zv AewnZ Kiv

- ‡mev`vbKvix I MÖnxZvi g‡a¨ Z_¨ Av`vb-cÖ`v‡bi gva¨‡g m¤ú‡K©I Dbœqb NUv‡bv

- ¯^v¯’¨ cÖwZôv‡bi Kvh©µ‡gi AMÖMwZ †`Lv‡bv

Kg©c×wZ:

- Z_¨ msMÖn K‡i Zvi h_vh_ g~j¨vq‡bi ci wbf©i‡hvM¨ Z_¨ cÖ`k©b Kiv

- cÖ‡Z¨K wefv‡M Zv‡`i wbR¯^ Z_¨¸‡iv Avjv`v Avjv`v fv‡e cÖ`k©bx †ev‡W©i gva¨‡g cÖ`k©b Kiv

- Z_¨ cÖ`k©‡bi †ÿ‡Î 5Gm KvB‡Rb bxwZgvjv AbymiY Kiv

- cÖwZwbqZ Z_¨ nvjbvMv` Kiv

- RvZxqfv‡e mviv †`‡k GKB ai‡Yi ¯^v¯’¨ cÖwZôv‡bi Rb¨ GKB ai‡Yi cÖ`k©b c×wZ Pvjy Kiv

`vwqZ¡mg~n:

- ‡mev`vbKvix‡`i wb‡R‡`i‡K Z_¨ msMÖn I Gi cÖ`k©‡bi ¸iæZ¡ m¤ú‡K© AewnZ nIqv

- ‡mev`vbKvix‡`i‡K Z_¨ †_‡K wm×všÍ MÖn‡Yi mÿgZv ˆZix Kiv

- RbMY‡K Z_¨ AewnZ Kiv

ev¯ÍevqbKvix

- ZË¡veavqK/BDGBPGdwcI I AvevwmK †gwWK¨vj Awdmvi

- cwimsL¨vb Kg©KZ©v

- WIT Gi mKj m`m¨ KZ…©K mg‡q mg‡q Kv‡Ri AMÖMwZ ch©v‡jvPbv

SOP Number: 12

SOP Title: চৌগাছা ও ঝিনাইদহ স্বাস্থ্য প্রতিষ্ঠান পরিদর্শনের মাধ্যমে বাস্তব জ্ঞান অর্জন করা

D‡Ïk¨:

- ‡mev`vbKvix I KwgDwbwU MÖæc‡K †PŠMvQv-wSbvB`n g‡Wj m¤ú‡K© ev¯Íe aviYv †`qv

- Kvh©µg mdjZvi `k©b AewnZ Kiv

- Kvh©µg ev¯Íevq‡bi ¸iæZ¡ I †KŠkj iß Kiv

Kg©c×wZ:

- ‡mev`vbKvix‡`i ga¨ n‡Z `vwqZ¡kxj I D‡`¨vMx gvbyl‡`i †ei Kiv

- KwgDwbwU mnvqZv MÖæ‡ci ga¨ n‡Z `vwqZ¡kxj I D‡`¨vMx gvbyl‡`i †ei Kiv

- G me e¨w³‡`i wb‡q ‡PŠMvQv-wSbvB`n cwi`k©‡b hvIqv

- ‡mLv‡b Zv‡`i mv‡_ gZ wewbg‡qi e¨e¯’v Kiv, Rbm¤ú„³ g‡Wj ev¯Íevq‡bi †KŠkj m¤ú‡K© AewnZ Kiv, Ges wbR wbR cÖwZôv‡b Zv ev¯Íevq‡bi Kg©‡KŠkj ˆZix Kiv

`vwqZ¡:

- ZË¡veavqK/BDGBPGdwcI I AvevwmK †gwWK¨vj Awdmvi, †dvKvj e¨w³

- KwgDwbwU mnvqZv MÖæ‡ci mfvcwZ

SOP Number: 13

SOP Title:	মডেল সম্পর্কে অভিজ্ঞ টেকনিকাল টিম গঠনের মাধ্যমে বিভিন্ন স্বাস্থ্য প্রতিষ্ঠানে মডেল হাতে কলমে বাস্তবায়ন করা

D‡Ïk¨:

- ‡PŠMvQv-wSbvB`n n‡Z evQvB Kiv AwfÁ e¨w³‡`i‡K †`‡ki wewfbœ †Rjv-Dc‡Rjv ¯^v¯’¨ cÖwZôv‡b nv‡Z Kj‡g g‡Wj m¤ú‡K© cÖwkÿY w`‡Z cvVv‡bv

- g‡Wj ev¯Íevqb‡K Av‡iv m„Rbkxj Kiv

- g‡Wj ev¯Íevq‡b wewfbœ c×wZ MV‡b mywbw`©ó f‚wgKv ivLv

Kg©c×wZ:

- ‡PŠMvQv-wSbvB`n n‡Z AwfÁ wPwKrmK, bvm©, IqvW© gv÷vi, GBPAvB, GmAvB-‡K wb‡q GKwU `j MVb Kiv

- cÖwkÿYv_©x cÖwZôvb wbe©vPb Kiv

- cÖwkÿ‡Yi mgqm~wP ˆZix Kiv

`vwqZ¡:

- Rbm¤ú„³ wm-‡R g‡Wj m¤úªmviY RvZxq †UKwbK¨vj KwgwU

SOP Number: 14

SOP Title:		KwgDwbwU mnvqZv MÖæc MVb Kiv

D‡Ïk¨:

- nvmcvZv‡ji gvbm¤§Z wPwKrmv Kvh©µg cwiPvjbv I Dbœq‡bi j‡ÿ¨ nvmcvZvj KZ…©cÿ‡K mnvqZv cÖ`vb

- miKvix Kvh©µg ev¯Íevq‡b Rb‡Mvôx‡K (Community) Kvh©Ki AskMÖnY Kiv‡bv

- miKvix m¤ú‡`i

- cvkvcvwk ¯’vbxq m¤ú`‡K ¯^v¯’¨ †mev Dbœq‡b mgvweó Kiv

- nvmcvZvj cwiPvjbvq Avw_©K I Ab¨vb¨ evavmg~n `~ixKi‡Y mnvqZv

- ¯^v¯’¨ †mev Dbœq‡b ¯’vbxq miKv‡ii Kvh©Ki AskMÖnY wbwðZ Kiv

- ¯^v¯’¨ †mev Dbœq‡bi P¨v‡jÄmg~n m¤ú‡K© ¯’vbxq †bZ…Z¡ I ¯’vbxq miKvix Kg©KZ©v‡`i‡K AewnZ Kiv I Gi †gvKv‡ejvq Zv‡`i‡K m¤ú„³ Kiv

- ¯^v¯’¨ †mev Kvh©µ‡g †mev`vbKvix I †mev MÖnxZv‡`i cvi¯úwiK Av¯’v I wbivc` cwi‡ek wbwðZ Kiv

- ¯^v¯’¨ †mev I ¯^v¯’¨ Dbœqb Kvh©µ‡g MZvbyMwZK AvgjvZvwš¿K `„wófw½i e`‡j mn‡hvwMZvg~jK I AskMÖnYg~jK e¨e¯’vcbv c×wZ AbymiY Kiv

Kg©c×wZ:

- nvmcvZv‡ji gvbm¤§Z †mev Kvh©µg cwiPvjbvi Rb¨ we‡kl K‡i wPwKrmvi cwi‡ek iÿv, cwi®‹vi cwi”QbœZv, k„sLjv I wbivcËv wbwðZKiY Kvh©µg cwiPvjbv I cwiPvjbvq nvmcvZvj KZ…©cÿ‡K mnvqZv cÖ`vb

- miKvix eivÏ I m¤ú‡`i m‡e©vËg e¨envi I iÿYv‡eÿY wbwðZKi‡Y nvmcvZvj KZ…©cÿ‡K mnvqZv cÖ`vb

- wPwKrmv †mevi Pvwn`v c~iY I Dbœq‡bi j‡ÿ¨ miKvix eiv‡Ïi cvkvcvwk ¯’vbxq `vZv I wn‰Zlx e¨w³ I cÖwZôvb‡K mswkøó Kiv Ges Zv‡`i mnvqZvq GKwU KwgDwbwU mv‡cvU© Znwej MVb Ges G welq cÖ`Ë wb‡`©kbv Abyhvqx Znwej cwiPvjbv

- wPwKrmv †mevi Pvwn`v c~i‡Y mgm¨v wPwýZ Kiv Ges ¯’vbxqfv‡e Zv mgvav‡bi j‡ÿ¨ c`‡ÿc MÖnY

- nvmcvZv‡j Kg©iZ wPwKrmK, bvm© I Ab¨vb¨ Kg©KZ©v Kg©Pvix‡`i †mev cÖ`v‡b Drmvn cÖ`vb Ges `vwqZ¡ cvj‡b MVbmg~jK civgk© cÖ`vb

`vwqZ¡:

- ‡Rjv‡Z wmwfj mvR©b/ZË¡veavqK

- Dc‡Rjv‡Z BDGBPGdwcI

SOP Number: 15

SOP Title:		Kvh©µ‡gi AMÖMwZ g~j¨vqb Kiv

D‡Ïk¨:

- †PŠMvQv- wSbvB`‡ni Av`‡k© Rbm¤ú„³ ¯^v¯’¨ e¨e¯’vcbv m¤úªmviY Kg©m~wPi D‡Ïk¨¸‡jv c~iY n‡”Q wK bv, Zv cwigvc Kiv

- G Av`k© ev¯Íevq‡b mswkøó GjvKvi gvby‡li ¯^v‡¯’¨i Dbœqb n‡”Q wK bv Zv cwgvc Kiv

Kg©c×wZ:

- AMÖMwZ g~j¨vq‡bi wb‡`©kK wba©viY Kiv

- wb‡`©kK Abyhvqx Z_¨ msMÖn Kiv

- Z_¨ we‡kølY K‡i cÖwZ‡e`b cÖ¯‘Z Kiv

- cÖwZ‡e`b AskxRb‡`i Kv‡Q weZiY Kiv

`vwqZ¡:

- †PŠMvQv- wSbvB`‡ni Av`‡k© Rbm¤ú„³ ¯^v¯’¨ e¨e¯’vcbv m¤úªmviY RvZxq †UKwbK¨vj KwgwU

SOP Number: 16

SOP Title:	‡PŠMvQv-wSbvB`n g‡W‡ji cÖwZôvZv‡`i G g‡Wj m¤úªmvi‡Y m¤ú„³ Kiv

D‡Ïk¨:

- g‡Wj cÖwZôvZv‡`i Ae`v‡bi ¯^xK…wZ †`qv

- Kg©Rxe‡b Zv‡`i AwfÁZvmg~n‡K g‡Wj m¤úªmvi‡Y Kv‡R jvMv‡bv

Kg©c×wZ:

- g‡W‡ji cÖwZôvZv‡`i ZvwjKv cÖ¯‘Z Kiv

- Zv‡`i‡K g‡Wj m¤úªmvi‡Y Kv‡R jvMv‡bvi Kg©cwiKíbv cÖ¯‘Z Kiv

`vwqZ¡:

- KvR m¤úv`‡bi Rb¨ RvZxq †UKwbK¨vj KwgwU GKwU Dc-KwgwU MVb Ki‡e

SOP Number: 17

SOP Title: cwi®‹vi cwi”QbœZv I †mŠ›`h© ea©b Kvh©µg

D‡Ïk¨:

- nvmcvZvj I Gi cvk¦©eZ©x GjvKvi cwi”QbœZv wbwðZ Kiv|

- nvmcvZvj mxgvbvi g‡a¨ evMvb ˆZix I †mŠ›`h© ea©b|

- nvmcvZvj cwi®‹vi cwi”QbœZvq †cŠimfv Z_v RbmvaviY‡K m¤ú„³ Kiv

- nvmcvZv‡ji ewniv½‡bi eR©¨ e¨e¯’vcbv Dbœqb Kiv

Kg©‡ÿÎ:

- nvmcvZvj cÖv½Y cwi®‹vi ivL‡Z RbMY‡K DrmvwnZ Kiv|

- nvmcvZv‡ji Uq‡jU/‡kŠPvMv‡ii cwi”QbœZv msiÿ‡Y †ivMx I Zv‡`i G‡Ub‡W›U‡`i m¤ú„³ Kiv

- nvmcvZvj cÖv½‡bi b`©gv wbqwgZ cwi®‹vi ivLv

- cvwÿK ev gvwmK wfwË‡Z RbM‡Yi AskMÖn‡Y nvmcvZvj cwi®‹vi Kiv|

- nvmcvZvj PZ¡‡i evMvb ˆZix

- mwâ evMvb K‡i cywói ¸iæZ¡ cÖ`k©b Kiv

- ‡flR evMvb K‡i †`kxq wPwKrmv c×wZ‡K DrmvwnZ Kiv

- emvi ¯’vb ˆZix Kiv|

- ‡mŠ›`h© ea©‡bi cÖ‡qvRbxq Ab¨vb¨ KvR Kiv

- ‰ÎgvwmK wfwË‡Z Õgnv cwi”QbœZv w`emÕ (Big Cleaning Day) cvjb Kiv

- K¨v¤úvm cwi®‹vi-cwi”QbœZv ivLvi cÖ‡qvRYxqZv m¤ú‡K© RbMY‡K m‡PZb Kiv

`vwqZ¦mg~n:

- RbMY‡K DrmvwnZ Kiv

- Rbm‡PZbZv ˆZix

- nvmcvZvj cwi®‹vi ivLvi cÖ‡qvRb m¤ú‡K© RbMY‡K m‡PZb Kiv

- nvmcvZv‡ji cwi®‹vi cwi”QbœZv eRvq ivL‡Z cÖ‡qvR‡b AvDU‡mvwm©s Gi wfwË‡Z Rbej wb‡qvM Kiv| KwgDwbwU mnvqZv Znwej n‡Z e¨q wbe©vn Kiv

Kvh©c×wZ:

- wZb/ Pvi m`m¨ wewkó Dc-KwgwU MVb|

- cwi”QbœZvi gv‡bvbœqb I †mŠ›`h© ea©‡bi Rb¨ KiYxq wel‡q wm×všÍ MªnY|

- m‡PZbZv e„w×‡Z c`‡ÿc MÖnY|

ev¯ÍevqbKvix:   WIT MVb Kiv

SOP Number: 18

SOP Title:	 mvwe©K wbivc` cwi‡ek wbwðZKiY Kvh©µg

D‡Ïk¨:

- nvmcvZv‡ji mvwe©K wbivcËv e¨e¯’vi `„k¨gvb DbœwZ K‡i wPwKrmv †mevi AbyK~j cwi‡ek ˆZix Kiv|

Kg©‡ÿÎ:

- nvmcvZv‡ji wPwKrmK I Ab¨vb¨ ‡mevKg©x, †ivMx I Zv‡`i AvZ¥xq ¯^Rb‡`i wbivcËv wbwðZ Kiv|

- nvmcvZvj cÖv½b `vjvjgy³ Kiv|

- ‡gwW‡Kj mvwU©wd‡KU cÖ`v‡b mywbw`©ó c×wZ AbymiY Kiv I cywjk ‡KBm mg~‡n AhvwPZ n¯Í‡ÿc I cÖfvweZ Kivi †Póv cÖwZnZ Kiv|

- nvmcvZv‡j AbvKvw•LZ cwiw¯’wZ Gov‡bvi Rb¨ c~&©v‡ýB Dchy³ e¨e¯’v †bqv, AbvKvw•LZ cwi‡ek m„wó n‡j Zv ZvrÿwYKfv‡e e¨e¯’vcbv Kiv|

- nvmcvZvj cÖv½b a~gcvb I gv`Kgy³ ivLvi wel‡q m‡e©v”P mZK© _vKv|

- nvmcvZv‡j Jla †Kv¤úvwbi cÖwZwbwa‡`i wbw`©ó mg‡q cÖ‡ekvwaKvi ‡`qv|

- wbivcËv ‡Rvi`vi Ki‡Z nvmcvZvj mxgvbv CCTV i AvIZvfz³ Kiv|

- Riæix wefv‡M AcÖ‡qvRbxq e¨w³‡`i hvZvqvZ wbqš¿Y Kiv|

`vwqZ¦mg~n:

- RbMY‡K DrmvwnZ Kiv|

- Rbm‡PZbZv ˆZix|

- ‡hme ¯’v‡b wbivcËvKgx©i Afve i‡q‡Q †mLv‡b ¯’vbxq e¨e¯’vcbvq wbivcËvKgx©i e¨e¯’v Kiv|

- AbvKvw•LZ cwiw¯’wZ †gvKv‡ejvq ¯’vbxq RbM‡Yi mgš^‡q ZvrÿwYK e¨e¯’vcbvi D‡`¨vM †bqv|

Kvh©c×wZ:

- wZb/ Pvi m`m¨ wewkó Dc-KwgwU MVb|

- m‡PZbZv e„w×‡Z c`‡ÿc MÖnY|

SOP Number: 19

SOP Title: ‡mev Kvh©µg

D‡Ïk¨:

nvmcvZv‡j †mevi mvwe©K gv‡bvbœqb|

Kg©‡ÿÎ:

- Riæix wefvM

- Riæix wefv‡M mve©ÿwYK ‡gwW‡Kj Awdmv‡ii Dcw¯’wZ‡Z (Dc‡Rjv‡Z Ab K‡j _vKv) wPwKrmv †mev wbwðZ Kiv|

- Riæix hš¿cvwZ (‡hgb: Aw·‡Rb, Møy‡KvwgUvi, †beyjvBRvi, RxevYygy³KiY hš¿), RxebiÿvKvix Jla Gi mieivn wbwðZ Kiv|

- ‡mvjvi wm‡÷g / AvBwcGm Gi gva¨‡g mve©ÿwYK we`y¨r mieivn wbwðZ Kiv|

- ewnwe©fvM:

- ewnwe©fv‡M ‡ivMx‡`i Rb¨ Af¨_©bv Kÿ/¯’vb ivLv|

- Mf©eZx gv, wkï, cyiæl, bvix‡`i Rb¨ c„_K wPwKrmv Kÿ ivLv

- gyw³‡hv×v Ges cÖexY‡`i Rb¨ we‡kl e¨e¯’v ivLv|

- ¯^v¯’¨ wkÿv, AvBGgwmAvB, GGbwm/wcGbwm, BwcAvB, †eª÷ wdwWs, IAviwU, GbwmwW, ˆK‡kvi ¯^v¯’¨ e¨e¯’v c„_K c„_K Kb©v‡ii gva¨‡g Kvh©Ki †mev †`qv

- cwi”Qbœ I‡qwUs iæg I jwe wbwðZ Kiv|

- wPwKrm‡Ki K‡ÿi mvg‡b myk„sLj e¨e¯’v M‡o †Zvjv|

- ewnwe©fv‡M AwWI-wfmyqvj gva¨‡g ¯^v¯’¨wkÿvi e¨e¯’v Kiv|

- ewnwe©fv‡M Jla †Kv¤úvwbi cÖwZwbwa‡`i wbw`©ó mg‡q cª‡ekvwaKvi †`qv|

- AšÍtwefvM:

- †mevi gvb e„w×‡Z c`‡ÿc MÖnY

- bvwm©s †mevi gvb e„w× I RbevÜe bvwm©s †mev wbwðZ Kiv

- mvÜ¨Kvjxb ivDÛ wbwðZ Kiv

- cÖme c~e©eZx©, cÖmeKvjxb I cÖme cieZx© †mevmg~n wbðZ Ki‡Z Mf©eZx bvix‡`i †iwR‡÷ªkb KvW© wbwðZ Kiv|

- ‡ivMx‡`i mKj cixÿv nvmcvZv‡jB m¤úbœ Kiv wbwðZ Kiv|

- ¯’vbxq RbMY‡K i³`v‡b DrmvwnZ Kiv I m¤¢ve¨ i³`vZv‡`i ZvwjKv msiÿY Kiv|

- weKj hš¿ `ªæZ †givg‡Zi e¨e¯’v †bqv| cÖ‡qvR‡b ¯’vbxq e¨e¯’vcbvq Kg Li‡P †givgZ m¤¢e n‡j Zvi e¨e¯’v †bqv|

- mve©ÿwYK G¤^y‡jÝ myweav wbwðZ Kiv| †Kvb Kvi‡Y G¤^y‡jÝ weKj n‡j ¯’vbxqfve †givg‡Zi e¨e¯’v Kiv †h‡Z cv‡i|

- nvmcvZv‡j mK‡ji Rb¨ wbivc` cvwbi e¨e¯’v wbwðZ Kiv|

- ‡kŠPvMvi mevi Rb¨ mnRjf¨ I cwi¯‹vi ivLv|

- Wv³vi‡`i wWDwU †iv÷vi I wmwU‡Rb PvU©vi cÖKvk¨ †bwUm †ev‡W© ¯’vcb|

`vwqZ¦ mg~n:

- nvmcvZv‡ji ‡mev Kvh©µg myôzfv‡e cwiPvjbvi Rb¨ RbMY‡K DrmvwnZ Kiv|

- Rbm‡PZbZv ˆZix|

Kvh©c×wZ:

- wZb/ Pvi m`m¨ wewkó Dc-KwgwU MVb|

- m‡PZbZv e„w×‡Z c`‡ÿc MÖnY|

SOP Number: 20

SOP Title: ‡ivM cÖwZ‡iva I wbqš¿Y

D‡Ïk¨:	gnvgvwi ev we‡kl ‡ivM Dc`ªæZ GjvKv‡Z we‡kl ¯^v¯’¨‡mevi e¨e¯’v ivLv I RbMY‡K m‡PZb Kiv

Kg©‡ÿÎ:

- gnvgvix ev Ab¨ †Kvb †iv‡Mi cÖv`yf©ve †`Lv w`‡j †m †ivM m¤ú‡K© m‡PZbZv ˆZixi Rb¨ †iv‡Mi jÿY, KviY, cÖwZKvi, cÖwZ‡iva e¨e¯’v m¤ú‡K© gvBwKs, e¨vbvi, ‡d÷z‡bi e¨e¯’v Kiv|

- cÖPvi Kv‡h© mvaviY RbMY‡K m¤ú„³ Kiv

`vwqZ¡mg~n:

- Rbm‡PZbZv ˆZwi

- RbMY‡K nvmcvZv‡ji †mev Kv‡h© m¤ú„³ Kiv

Kvh©c×wZ:

- wZb/ Pvi m`m¨ wewkó Dc-KwgwU MVb

SOP Number: 21

SOP Title :  Jla mieivn e¨e¯’vcbv

D‡Ïk¨t

- nvmcvZv‡ji mvwe©K †mevi mvwe©K gvb Dbœqb

Kg©‡ÿÎt

- Jla mieivn wbqwgZ I wbiwew”Qbœ Kiv

- miKvwi Jl‡ai mwVK e¨envi wbwðZ Kiv

- AwZ cÖ‡qvRbxq Jl†ai miKvwi mieivn †kl n‡j ¯’vbxqfv‡e µ‡qi e¨e¯’v Kiv

`vwqZ¡ mg~n t

- Rbm‡PZbZv ˆZwi

- RbMb‡K nvmcvZv‡ji †mev Kv‡h© m¤ú„³ Kiv

Kvh©c×wZt

- wZb/ Pvi m`m¨ wewkó Dc-KwgwU MVb

SOP Number :22

SOP Title:  c_¨ mieivn e¨e¯’vcbv

D‡Ïk¨ t

- nvmcvZv‡ji mvwe©K gvb Dbœq‡b Awf‡hvM I civgk© ev· ¯’vcb K‡i RbmvaviY‡K m¤ú„³ K‡i †mevi mvwe©K gvb Dbœqb

Kg©‡ÿÎ t

- nvmcvZv‡j mieivnK…Z c‡_¨i ¸YMZ gvb wbwðZ Kiv

- nvmcvZv‡ji ivbœNi Gi cwi®‹vi cwi”QbœZv wbwðZ Kiv

- nvmcvZv‡j mevi Rb¨ wbivc` cvwbi mieivn wbwðZ Kiv

`vwqZ¡ mg~n t

- Rbm‡PZbZv ˆZwi

- RbMb‡K nvmcvZv‡ji †mev Kv‡h© m¤ú„³ Kiv

Kvh©c×wZ t

- wZb/ Pvi m`m¨ wewkó Dc-KwgwU MVb

SOP Number: 23

SOP Title:  Awf‡hvM wb®úwËKiY Kvh©µg

D‡Ïk¨ t

- nvmcvZv‡ji mvwe©K gvb Dbœq‡b Awf‡hvM I civgk© ev· ¯’vcb K‡i RbmvaviY‡K m¤ú„³ K‡i †mevi mvwe©K gvb Dbœqb

Kg©‡ÿÎ t

- nvmcvZv‡ji cÖ‡ek c‡_ Awf‡hvM I civgk© ev· ¯’vcb Kiv

- Awf‡hvMKvixi bvg/cwiP‡qi †MvcbxqZv iÿv Kiv n‡e

- mvßvwnKfv‡e Awf‡hvM I civgk© Abyhvqx `ªæZ e¨e¯’v MÖnY

`vwqZ¡ mg~nt

- Rbm‡PZbZv ˆZwi

- RbMY‡K nvmcvZv‡ji †mev Kv‡h© m¤ú„³ Kiv

Kvh©c×wZ t

- wZb/ Pvi m`m¨ wewkó Dc-KwgwU MVb

SOP Number : 24

SOP Title:  Z_¨ I †hvMv‡hvM cÖhyw³ e¨e¯’vcbv

D‡Ïk¨t

- nvmcvZv‡ji mvwe©K gvb Dbœq‡b ICT Gi gva¨‡g RbmvaviY‡K m¤ú„³ K‡i †mevi mvwe©K gvb Dbœqb

Kg©‡ÿÎ t

- nvmvcvZv‡ji mgm¨v mgvav‡b B‡jKUªwbK wgwWqvi mvnv‡h¨ †bIqv

- wbivcËv †Rvi`vi Ki‡Z nvmcvZvj mxgvbv CC Camera AvIZvfy³ Kiv

- mve©ÿwYK Riæix ‡ní jvBb mvwf©m Pvjy Kiv

- Riæix †Uwj‡gwWwmb †mev cÖ`vb

- ¯^v¯’¨ wkÿvi cÖmv‡i AbjvBb wgwWqvi gva¨‡g RbmvaviY‡K KwgwU‡Z KvR Kivi e¨vcv‡i Drmvn cÖ`vb

- nvmcvZv‡ji †ivMx‡`i Z_¨vw` wWwRUvj bw_c‡Îi gva¨‡g msiÿY

- AwWI-wfmyqvj gva¨‡g I‡qwUsiæ‡g/ A‡cÿv N‡i ¯^v¯’¨ Z_¨ cÖ`vb|

`vwqZ¡ mg~n t

- Rbm‡PZbZv ˆZwi|

- RbMb‡K nvmcvZv‡ji †mev Kv‡h© m¤ú„³ Kiv|

Kvh©c×wZ t

- ICT Gi gva¨‡g m‡PZbZv e„w×‡Z c`‡ÿc MÖnY|

- wZb/ Pvi m`m¨ wewkó Dc-KwgwU MVb

Building Blocks of C-J Model:

| Sl.No. | Criteria of Chowgacha Model | Very good | Good | Poor |
| --- | --- | --- | --- | --- |
| 1. | Birth &Death recording |  | + |  |
| 2. | Health education Corner. |  |  | + |
| 3. | Cleanliness & Beautification |  | + |  |
| 4. | Cycle-Van stand close to the main gate. |  | + |  |
| 5. | Display of the activities of the UHC (Field &health complex.) |  |  | + |
| 6. | Blood donor list in Pathology dept |  | + |  |
| 7. | Separation of patient in OPD &IPD (Male, Female, Under5 & EOC) |  | + |  |
| 8. | IMCI-Corner. |  | + |  |
| 9. | ANC&PNC Corner |  | + |  |
| 10. | NCD-Corner |  | + |  |
| 11. | EPI & Breast-Feeding Corner |  |  | + |
| 12. | ORT &Nutrition Corner |  |  | + |
| 13. | Waste management |  | + |  |
| 14. | Moral based environment. |  | + |  |
| 15. | Implimentation of 5S KAIZEN |  | + |  |
| 16. | Community participation |  |  | + |
| 17. | Reception Desk | + |  |  |
| 18. | Hospital Protocol board. |  |  | + |
| 19. | Display of meeting schedule |  |  | + |
| 20. | Knowledge about 7th5 yr. Plan & SDG. |  |  | + |
| 21. | Display of information in every section |  |  | + |
| 22. | VIA Service |  | + |  |
| 23. | Infection prevention activities. |  | + |  |
| 24. | Relation with local administration, OC & community leaders. |  | + |  |
| 25. | Positive media coverage |  | + |  |
| 26. | Publication of Annual Report. |  |  | + |
| 27. | Position in HSS score of MIS in Feb-22. |  |  | 237th |
| 28 | Video on UHC. |  |  | + |

WIT: 1				(EOC Ward)

Step 1:Selection of Kaizen theme with feasibility check with Matrix Diagram

| Possible KAIZEN Theme | Impact to patient outcome | Affordable in terms of time and resources | Easy to measure | Under control of team members. | Total Score |
| --- | --- | --- | --- | --- | --- |
| Implementation of partograph | 5 | 3 | 3 | 4 | 15 |
| Improve infection prevention | 5 | 3 | 2 | 2 | 12 |
| Improve labor room service with added component | 5 | 5 | 5 | 4 | 19 |
| Improve post-operative care among the operated patient | 4 | 4 | 3 | 3 | 14 |
| Maintain proper temperature, pulse, BP in the word | 4 | 4 | 4 | 5 | 17 |

Step 2: Situation analysis

Kaizen theme: Labor room service improved with comprehensive services components.

Data collection method: Data collected by a WIT member through exit interview of 100 women who delivered in consecutive 20 days from 4th to 24th September.

| Sl No | Contributing factors | Frequency | Cumulative frequency | Cumulative % |
| --- | --- | --- | --- | --- |
| 1 | Sterile delivery set not used properly | 34 | 34 | 40% |
| 2 | Labor room sister is not available. | 15 | 49 | 63% |
| 3 | Chlorine solution is not used properly | 12 | 61 | 71% |
| 4 | Counseling is not done | 10 | 71 | 84% |
| 5 | Medical officer/Consultant is not supervise every case | 6 | 77 | 90% |
| 6 | Labor room lighting system not functioning effectively | 5 | 82 | 96% |
| 7 | Privacy is not maintained properly | 3 | 85 | 100% |

Step 3: Root cause analysis (Fishbone diagram):

Sterile delivery set not used properly

Job description is not developed

Not purched the set

Initiative not taken

SOP not collected

Not available in store

Demand not given

Number of delivery set is limited

Division of  labor not done

Overload of the patients

Limited  manpower

Authority was not informed

Unwanted articles not removed

Proper space is not available

Lack of knowledge about sterility

Lack of SOP

Lack of importance about extra set

Sterile delivery set not used properly

Man

Material

Environment

Method

| Root cause | Primary action | Secondary action | Importance | Urgency | Difficulty | Time consumption | Resource availability | Total score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No initiative for extra manpower | Initiative for extra manpower | Identify the extra manpower | 4 | 3 | 2 | 2 | 1 | 12 |
|  |  | Rearrangement of manpower | 2 | 2 | 1 | 2 | 2 | 9 |
| Delivery set was not available | Arrangement of good quality of delivery set | Purchase of delivery set | 3 | 3 | 2 | 2 | 2 | 12 |
|  |  | Identify good quality of delivery set | 3 | 3 | 2 | 2 | 2 | 12 |
| No SOP for using sterility of delivery set | Arrangements of SOP for using sterile sets | Collection of SOP for sterility module | 3 | 3 | 2 | 3 | 3 | 14 |
|  |  | pre and post training arrangement | 3 | 3 | 3 | 2 | 2 | 13 |
| Less number of nurses | Arrangement of extra nurses | Posting of new nurses | 3 | 3 | 2 | 2 | 2 | 12 |
|  |  | rearrangement of nurses | 3 | 3 | 3 | 2 | 3 | 14 |
| No initiative of fund for sitting arrangement | Initiative for fund for sitting arrangement | Identify the probable cost of the chairs | 3 | 2 | 2 | 2 | 2 | 11 |
|  |  | Identify the donors for the support | 3 | 3 | 3 | 2 | 1 | 12 |
| Not taken initiative for good quality chlorine solution | Indenting of good quality chlorine solution | Purchase of chlorine solution | 3 | 3 | 2 | 2 | 2 | 12 |
|  |  | Orientation about the use of the solution | 3 | 2 | 1 | 2 | 2 | 10 |
|  |  | Identify the person supervises regularly | 3 | 2 | 2 | 2 | 2 | 11 |
| Initiative not taken for supervision of sterility | Organize regular supervision system | Make a checklist for quality investigation | 3 | 3 | 3 | 2 | 2 | 13 |
|  |  | Ensure regular on-the-job training | 3 | 3 | 3 | 2 | 2 | 13 |
| Initiative not taken for counseling | Arrange effective counseling system | Identify the points for counseling | 3 | 3 | 3 | 2 | 2 | 13 |
|  |  | Regular monitoring the system of counseling | 3 | 3 | 2 | 2 | 2 | 12 |

Step 4: Identification of actions/countermeasures

Step 5: Implementation of actions/countermeasures: action plan and progress monitoring for EOC ward (WIT-1)

| Sl | Actions | Where | Who | When | Date of monitoring | Who | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Identify the extra manpower | EOC ward | Consultant | 20 to 30 Oct | 28 Oct | RMO |  |
| 2 | Purchase of delivery set | EOC ward | Hospital Super | 30 Oct to 15 Nov | 10 Nov | Super |  |
| 3 | Collection of SOP | EOC ward | Consultant | 15 to 20 Nov | 18 Nov | Focal Person |  |
| 4 | Posting of extra nurses | EOC ward | Hospital super | 20 to 30 Oct | 25 Oct | Focal Person |  |
| 5 | Initiative for fund | EOC ward | Consultant | 25 Oct to 5 Nov | 30 Oct | RMO |  |
| 6 | pre and post training arrangement | EOC ward | Store keeper | 25 Oct to 15 Nov | 30 Oct | RMO |  |
| 7 | Identify the points for counseling | EOC ward | Hospital super | 15 Oct to 20 Nov | 17 Nov | Focal Person |  |
| 8 | Regular monitoring the system of counseling | EOC ward | Team Leader | 15 Nov to 20 Nov | 17 Nov | Focal Person |  |
| 9 | Purchase of chlorine solution | EOC ward | Hospital super | 25 Oct to 10 Nov | 5 Nov | Super |  |
| 10 | Initiative taken for supervision | EOC ward | Hospital Super | 30 Oct to 15 Nov | 10 Nov | Super |  |

Step 6: Effectiveness of actions/countermeasures

| Sl No | Contributing factors | Frequency |  | Frequency Reduction | Reduced% |
| --- | --- | --- | --- | --- | --- |
|  |  | Before PDCA | After PDCA |  |  |
| 1 | Sterile delivery set not used properly | 34 | 10 | 24 | 71% |
| 2 | Labor room sister is not available. | 15 | 3 | 12 | 80% |
| 3 | Chlorine solution is not used properly | 12 | 2 | 10 | 83% |
| 4 | Counseling is not done | 10 | 3 | 7 | 70% |
| 5 | Medical officer/Consultant is not supervising every case | 6 | 1 | 5 | 83% |
| 6 | Labor room lighting system not functioning effectively | 5 | 1 | 4 | 80% |
| 7 | Privacy is not maintained properly | 3 | 0 | 3 | 100% |